## Runbook
17th March 2026
Migration Runbook- Fraserhealth.ca Website
Planned Start Date | Planned end date | T-Minus | Actual Start Date | Actual end date | Delay | Activities | Duration (in Minutes) | Status | KPMG | FHA | PHSA | App team | Microsoft | Dependencies | Comments | Assumption
2025-11-06 | 2025-11-06 | -93 | 2025-11-06 | 2025-11-18 | 11 - days | App Owner KickOff meeting |  | Completed
2025-11-06 | 2025-11-06 |  | 2025-11-06 | 2025-11-06 |  | Provide an overview of the migration project, including its goals, scope, key milestones, roles and responsibilities. |  | Completed | R | A |  | C,I
2025-11-06 | 2025-11-06 |  | 2025-11-17 | 2025-11-18 |  | Send the application intake form to the application team. |  | Completed | R,A | C,I |  | R
2025-11-17 | 2025-11-20 | -78 | 2025-11-17 | 2025-11-21 | 1 - day | App Intake and Assess current state architecture |  | Completed
2025-11-17 | 2025-11-18 |  | 2025-11-17 | 2025-11-17 |  | Gather details on the existing infrastructure, architecture, and any dependencies. |  | Completed | A | C,I | C,I | R |  | KPMG is dependent on the application team
2025-11-18 | 2025-11-20 |  | 2025-11-19 | 2025-11-21 |  | Evaluate the current architecture, dependencies, hardware/software requirements, and performance of each application. |  | Completed | C,I | A | C | R |  | KPMG is dependent on the application team and FHA
2025-12-12 | 2026-01-06 | -54 | 2026-01-22 | 2026-01-22 | 11 - days | Initial Communication to all (FHA/AppOwners/MS) |  | Completed
2025-12-12 | 2026-01-06 |  | 2026-01-22 | 2026-01-22 |  | Send out a formal communication regarding the migration events,dates planned and requesting the app team to prepare the UAT test cases. |  | Completed | R,A | I |  | C,I | I
2024-12-06 | 2026-01-07 | -50 | 2025-12-12 | 2026-01-16 | 8 - days | Target state Architecture review and approval (Non-Prod) |  | Completed
2024-12-06 | 2025-12-06 |  | 2025-12-12 | 2025-12-12 |  | Create reference target architecture - Subscription design, Network design and application infrastructure. |  | Completed | R,A | I | I | I | C
2026-01-07 | 2026-01-07 |  | 2025-12-18 | 2026-01-16 |  | Reference Architecture design review and Signoff |  | Completed | C,I | R,A | R | R | C | KPMG is dependent on the application team and FHA to provide signoff
2026-01-07 | 2026-01-09 | -47 | 2025-12-22 |  | 0 | Approval Mail from App Owner for Non Prod Migration |  | Inprogress
2026-01-07 | 2026-01-08 |  | 2025-12-22 | 2025-12-22 |  | Send out a formal communication regarding the migration events,dates planned and requesting the app team to approve it |  | Completed | R,A | I |  | C,I | I
2026-01-08 | 2026-01-09 |  | 2025-12-23 |  |  | Get the confirmation mail from the app owner about the migration date |  | Inprogress | R | A | C,I |  | I | KPMG is dependent on the microsoft team to setup the azure migrate appliance
2026-01-12 | 2026-01-14 | -42 | 2026-01-19 | 2026-01-28 |  | Azure Platform setup -Non Prod |  | Completed
2026-01-12 | 2026-01-14 |  | 2025-11-12 | 2025-11-12 |  | Creation of Subscription(s) |  | Completed | A | R | I | I | C,I | KPMG team will be dependent on Landing Zone Creation
2026-01-12 | 2026-01-14 |  | 2026-01-19 | 2026-01-19 |  | Deploy application specific Resource Group |  | Completed | R,A | I | I |  | C
2026-01-12 | 2026-01-14 |  | 2025-11-12 | 2025-11-12 |  | Creation of Target Vnet |  | Completed | C,I | R,A | I | I | C | KPMG team will be dependent on Landing Zone Creation
2026-01-12 | 2026-01-14 |  | 2026-01-27 | 2026-01-28 |  | Creation of Target IP |  | Completed | R,A | I | I |  | C
2026-01-12 | 2026-01-14 |  | 2026-01-20 | 2026-01-21 |  | Provision the Isolated Vnet for testing |  | Completed | C,I | R,A | I | I | C | KPMG team will be dependent on Landing Zone Creation
2026-01-12 | 2026-01-14 |  | 2025-11-12 | 2025-11-12 |  | Provision application/web/DB subnets |  | Completed | C,I | R,A | I | I | C | KPMG team will be dependent on Landing Zone Creation
2026-01-12 | 2026-01-14 |  | 2025-11-12 | 2025-11-12 |  | Creation of application gateway |  | Completed | C,I | R,A | I | I | C | KPMG team will be dependent on Landing Zone Creation
2026-01-12 | 2026-01-14 |  | 2026-01-19 | 2026-01-19 |  | Provision the Azure Key Vault |  | Completed | R,A | I | I | C,I | C,I
2026-01-12 | 2026-01-14 |  | 2026-01-19 | 2026-01-19 |  | Provision the Azure Recovery Services Vault and configure backup policies for the application |  | Completed | R,A | I | I | I | I
2026-01-12 | 2026-01-14 |  | 2026-01-19 | 2026-01-19 |  | Configure Backup Policies |  | Completed | R,A | I | I | I | I
2026-01-12 | 2026-01-14 | -42 | 2026-01-19 | 2026-01-28 |  | Pre- Migration Checklist |  | Inprogress
2026-01-12 | 2026-01-14 |  |  |  |  | Check SanDisk Policy ( if it is offline , inform customer to make online) - Need to be communicted with PHSA |  | Yet-to-start | A | I | R | I | C | KPMG is dependent on PHSA Team
2026-01-12 | 2026-01-14 |  |  |  |  | Need to check the RG locks. Resource Group locks should not be locked at the time of migration but can be enabled after migration is complete to prevent accidental deletion or modification of resource groups and resources. |  | Yet-to-start | A | C,I | C,I | I | R | KPMG is dependent on Microsoft team
2026-01-12 | 2026-01-14 |  |  |  |  | Check subscription quotas if a quota is exceeded, deployments or migrations will fail until quota is increased |  | Yet-to-start | A | C,I | C,I | I | R | KPMG is dependent on Microsoft team
2025-12-16 | 2026-01-19 | -41 | 2025-12-19 | 2026-01-16 | 0 | Migration Runbook - Review & Approval(Non-prod) |  | Completed
2025-12-16 | 2025-12-18 |  | 2025-12-17 | 2025-12-17 |  | Create the Migration Runbook |  | Completed | R,A | I | I | I | C
2025-12-18 | 2025-12-19 |  | 2025-12-19 | 2026-01-16 |  | Get the Migration runbook reviewed & Signoff |  | Completed | A | R | I | I | C,I | KPMG is dependent on the application team and FHA to provide signoff
2025-12-18 | 2026-01-19 | -41 |  |  |  | Notify MS to Initiate the Replication of servers in Azure Migrate |  | Yet-to-start
2025-12-18 | 2026-01-19 |  |  |  |  | Select servers for replication in Azure Migrate. |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2025-12-18 | 2026-01-19 |  |  |  |  | Configure replication settings (target region, resource group,VNet,Avalialblity Zone,Vm Size etc). |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2025-12-18 | 2026-01-19 |  |  |  |  | Start initial replication to Azure. |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2025-12-18 | 2026-01-19 |  |  |  |  | Monitor replication until status is Healthy. |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-01-23 | 2026-01-27 | -36 | 2026-01-20 |  |  | Firewall Opening Request, Local User Account & Server Restart Request |  | Inprogress
2026-01-23 | 2026-01-24 |  | 2026-01-20 |  |  | Send Request to PHSA to create the Local User account & Restart the server |  | Inprogress | R,A | I | I | I | I
2026-01-24 | 2026-01-25 |  | 2026-01-20 |  |  | Send Request to PHSA to open the required firewall ports |  | Inprogress | C | A | R | I | I | KPMG is dependent on PHSA and FH
2026-01-25 | 2026-01-27 |  | 2026-01-20 |  |  | Create Local User Account |  | Inprogress | C | A | R | I | I | KPMG is dependent on PHSA and FH
2026-01-27 | 2026-01-27 |  | 2026-01-20 |  |  | Restart Servers |  | Inprogress | C | A | R | I | I | KPMG is dependent on PHSA and FH
2026-01-28 | 2026-01-28 | -34 |  |  |  | Test-Migration execution of Non prod |  | Yet-to-start
Migration bridge will be live on Teams during the test migration -- relevant team members must join - All the below activities will be performed during the call
2026-01-28 | 2026-01-28 |  |  |  |  | Initiate test Migration for replicated servers |  | Yet-to-start | A | I | I | I | R | KPMG is dependent on Microsoft team
2026-01-28 | 2026-01-28 |  |  |  |  | Choose Isolated test virtual network |  | Yet-to-start | A | I | I | I | R | KPMG is dependent on Microsoft team
2026-01-28 | 2026-01-28 |  |  |  |  | Montior the test migration Job and validate the test VM created with test-servername,drives and nic validation |  | Yet-to-start | A | I | I | I | R | KPMG is dependent on Microsoft team
2026-01-28 | 2026-01-28 |  |  |  |  | Check able to login with local credentials as domain will not be join during test migration -- During Test Migration MS will validate the local credentials |  | Yet-to-start | A | C,I | C,I |  | R | KPMG is dependent on Microsoft team
2026-01-28 | 2026-01-28 |  |  |  |  | Login to server in test virtual network via bastion to validate Local credentials Note:Bastion, RDP needs to be enabled on test virtual network which has dependency with PHSA/FH |  | Yet-to-start | A | C,I | C,I |  | R | KPMG is dependent on FH
2026-01-31 | 2026-02-03 | -32 | 2025-11-12 |  |  | VM smoke test(Infrastructure Level) |  | Yet-to-start
2026-01-31 | 2026-01-31 |  | 2025-11-12 | 2025-11-12 |  | Configure Bastion Host to provide access to Vms. |  | Completed | I | R,A | I | I | C,I
2026-02-01 | 2026-02-01 |  |  |  |  | Validate the server is up & running, VM boot diagnostics and IP attached. |  | Yet-to-start | A | I | I | I | R | KPMG is dependent on Microsoft team
[6 empty] | Check the performance of the server.(This is not required as application team will highlight if any application performance issue observed) |  | Yet-to-start | R | I | I | A | C | KPMG is dependent on Application Team
2026-02-01 | 2026-02-01 |  |  |  |  | Perform Infra level test on migrated VMs -Validate if they can access server with the local account, and server boot status and boot diagnostics details needs to be captured by MS |  | Yet-to-start | R,A | I | I |  | R | KPMG is dependent on Microsoft team
2026-02-03 | 2026-02-03 |  |  |  |  | Delete test VM after validation. |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-03 | 2026-02-03 |  |  |  |  | Confirm replication remains intact for final migration. |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-03 | 2026-02-05 | -30 |  |  |  | Notify users/app team for downtime |  | Yet-to-start
2026-02-03 | 2026-02-05 |  |  |  |  | Send out a formal communication regarding the cutover and the unavailability of the application during the timeframe. |  | Yet-to-start | R,A | I | I | C,I | I
2026-02-06 | 2026-02-08 | -29 |  |  |  | Validate the Replication status is healthy and ensure there are no critical errors prior to the day before migration |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 | -25 |  |  |  | Non-Prod Migration Execution |  | Yet-to-start
2026-02-09 | 2026-02-09 |  |  |  |  | Stop any scheduled backups or jobs on the source VM if required for consistency. |  | Yet-to-start | I | I | R,A | R | I | KPMG is dependent on PHSA and App team
2026-02-09 | 2026-02-09 |  |  |  |  | Perform final backup of on-premise Non-prod servers |  | Yet-to-start | C,I | C,I | R,A | R | I | KPMG is dependent on PHSA and App team
2026-02-09 | 2026-02-09 |  |  |  |  | Verify replication status is Healthy in Azure Migrate. | 10 | Yet-to-start | C,I | I | I |  | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Validate the target settings like : Target region,RG,VMSIZE,Zone,Target Vnet,Subnet mainly | 15 | Yet-to-start | R | C,I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Make sure that atleast one member of on-prem domain admins involved in migration have rdp access to azure migrated VMs (This is required, so that domain admins can login to azure vm post migration and add the machine to the domain | 15 | Yet-to-start | C,I | C,I | R,A |  | I | KPMG is dependent on PHSA
2026-02-09 | 2026-02-09 |  |  |  |  | In Azure Migrate, select the replicated server and choose Migrate → Cutover. | 5 | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Select Shutdown source VM option in Azure Migrate | 10 | Yet-to-start | C,I | I | R | I | R,A | KPMG is dependent on PHSA to shut down on-prem servers
2026-02-09 | 2026-02-09 |  |  |  |  | Start the cutover process; Non- prod DB and Web Servers (SDAPPRESP001, SDDBSRESP001) Azure will create the VM in the target resource group and virtual network as per the replicated settings defined earlier. | 60 | Yet-to-start | C,I | C,I | C,I | I | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Validate the new VM created in Azure Portal | 10 | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Validate Boot status is up and running | 15 | Yet-to-start | R | I | I |  | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Replace the NIC on the migrated VM with the exsiting original static IP by removing the NIC that was automatically created during migration | 30 | Yet-to-start | C,A | I |  | I | R | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Rollback - For Roll back please refer to the Rollback steps section in the T-Zero Cutover Activities tab. | 30 | Yet-to-start | R | C,I | R,A | R | R | KPMG is dependent on PHSA, Microsoft and App team
2026-02-09 | 2026-02-09 | -25 |  |  |  | Post Migration Activities |  | Yet-to-start
2026-02-09 | 2026-02-09 |  |  |  |  | Once the vm is migrated successfully and power down, please change the memory to 4 MB. This will prevent the vm to be powered on by accident. | 30 | Yet-to-start | I | R,A
2026-02-09 | 2026-02-09 |  |  |  |  | Post-migration on vCenter, the vCenter administrators should rename the server display name extenstion to .amig and uncheck the NIC. This step is required immediately after migration; otherwise, HARDNS or DRS may automatically initiate a power-on | 30 | Yet-to-start | I | R,A
2026-02-09 | 2026-02-09 |  |  |  |  | Attach VMs to the backup Policies | 30 | Yet-to-start | A | R |  | I | C | KPMG is dependent on PHSA/FH Team
[6 empty] | Enabling Azure Monitor / Log Analytics if monitoring is required | 30 | Yet-to-start | A | R |  | I | C | KPMG is dependent on PHSA/FH Team
2026-02-09 | 2026-02-09 |  |  |  |  | Delete the Vmware Tools and any other softwares that are not required. Script can be provided by MS, any changes to the script has to be made along with the permission to run it in azure | 15 | Yet-to-start | A | C,I | I | I | R | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Verify the integrity and completeness of data migrated to Azure | 15 | Yet-to-start | R | C,I | I | R | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | After migration, Domain Admin or Local Admin logs in to migrated Azure servers to validate the authentication of the credntials | 30 | Yet-to-start | C,I | C,I | R,A | R | C,I | KPMG is dependent on PHSA and App team
2026-02-09 | 2026-02-09 |  |  |  |  | Perform Infralevel testing once vm created using Local admin account |  | Yet-to-start | R,A | I | I | I | C,I
2026-02-09 | 2026-02-09 |  |  |  |  | Modify DNS entry for the Azure Vms with their private ip (if required) | 30 | Yet-to-start | C,I | C,I | R,A | I | C,I | KPMG is dependent on PHSA
2026-02-09 | 2026-02-09 |  |  |  |  | Join the VMs to Domain | 30 | Yet-to-start | C,I | C,I | R,A | I | I | KPMG is dependent on PHSA
2026-02-09 | 2026-02-09 |  |  |  |  | Verify the ports and firewall rule on NSG for the Azure migrated DB and Web server | 15 | Yet-to-start | R,A | I | I |  | C,I
2026-02-09 | 2026-02-09 |  |  |  |  | Update integration configuration to point to the new cloud application | 20 | Yet-to-start | C,I | A | I | R | C,I | Kpmg is dependent on app team and FHA
2026-02-09 | 2026-02-09 |  |  |  |  | Ensure user have been granted access to the newly migrated applications | 10 | Yet-to-start | I | A | C,I | R | I | Kpmg is dependent on app team and FHA
2026-02-09 | 2026-02-09 |  |  |  |  | Add the vm to to backendpool of any loadbalancer if required,Associate NSG,ASG | 20 | Yet-to-start | R,A | R |  | I | C,I
2026-02-09 | 2026-02-09 |  |  |  |  | Verify access to the vendor/application team |  | Yet-to-start | C | C | I | R,A | I | Kpmg is dependent on app team |  | The application team will be deploying the application and they will login into the VM via Bastion using their domain ID
2026-02-09 | 2026-02-09 |  |  |  |  | If any, reconfigure the Connection strings, integrations to point to the new environment. This might involve updating API endpoints, re-authenticating, or changing configurations. |  | Yet-to-start | C,I | C,I | I | R,A | I | Kpmg is dependent on app team
2026-02-09 | 2026-02-09 |  |  |  |  | Conduct end-to-end testing of each integration to verify they are working as expected. |  | Yet-to-start | C,I | C,I | I | R,A | I | Kpmg is dependent on app team
2026-02-09 | 2026-02-09 |  |  |  |  | Ensure UAT test cases are created upfront to perform the testing |  | Yet-to-start | C,I | C,I | I | R,A | I | Kpmg is dependent on app team
2026-02-09 | 2026-02-09 |  |  |  |  | Execute test cases and document results. |  | Yet-to-start | C,I | C,I | I | R,A | I | Kpmg is dependent on app team
2026-02-09 | 2026-02-09 |  |  |  |  | Document any issues or deviations found during the testing process |  | Yet-to-start | C,I | C,I | I | R,A | I | Kpmg is dependent on app team
2026-02-09 | 2026-02-09 |  |  |  |  | Request Partial Sign off from app owners (One week lead time to validate the performance testing to provide the complete sign off) |  | Yet-to-start | R,A | I | I |  | C,I
2026-02-09 | 2026-02-12 | -23 |  |  |  | Performance & Application Stability testing by application team |  | Yet-to-start
2026-02-09 | 2026-02-12 |  |  |  |  | One week lead time to montior the performance & Stability of the application by app owners |  | Yet-to-start | C,I | C,I | I | R,A | I | Kpmg is dependent on app team
2026-02-09 | 2026-02-12 | -23 |  |  |  | User Acceptance Prod Env & Notify Stakeholders of Successful Migration |  | Yet-to-start
2026-02-09 | 2026-02-12 |  |  |  |  | Get the UAT signoff & Communicate all the stakeholders about the successful migration. |  | Yet-to-start | R,A | I | I | I | I
2026-02-14 | 2026-02-14 | -21 |  |  |  | Stop replication in Azure Migrate to finalize migration only after we receive signoff by application team | 10 | Yet-to-start | C,I | I |  |  | R,A | KPMG is dependent on Microsoft team
Prod Activities
2025-12-06 | 2026-02-13 | -22 | 2025-12-12 | 2026-01-16 |  | Target state Architecture review and approval (Prod) |  | Completed
2025-12-06 | 2025-12-24 |  | 2025-12-12 | 2025-12-12 |  | Create reference target architecture - Subscription design, Network design and application infrastructure. |  | Completed | R,A | I |  | I | C
2025-12-24 | 2026-02-13 |  | 2025-12-18 | 2026-01-16 |  | Reference Architecture design review and Signoff |  | Completed | C,I | R,A | R | R | C | KPMG is dependent on the application team and FHA to provide signoff
2026-02-13 | 2026-02-16 | -21 | 2026-01-22 | 2026-01-22 |  | Creation of MOP/Review & Signoff(Prod) |  | Completed
2026-02-13 | 2026-02-16 |  | 2026-01-22 | 2026-01-22 |  | Document MOP for RFC creation |  | Completed | R | A | C,I |  | I
2026-02-16 | 2026-02-17 | -20 |  |  |  | RFC Creation & Approval (Prod) |  | Yet-to-start
2026-02-16 | 2026-02-17 |  |  |  |  | Creation of RFC for prod |  | Yet-to-start | R | A | C,I |  | I
2026-01-17 | 2026-02-20 | -17 | 2025-11-12 | 2026-01-28 |  | Azure Platform setup -Prod |  | Completed
2026-01-17 | 2026-02-20 |  | 2025-11-12 | 2025-11-12 |  | Creation of Subscription(s) |  | Completed | A | R | I | I | C,I | Depending on Landing Zone Creation
2026-01-17 | 2026-02-20 |  | 2026-01-28 | 2026-01-28 |  | Deploy application specific Resource Group |  | Completed | R,A | I | I |  | C
2026-01-17 | 2026-02-20 |  | 2025-11-12 | 2025-11-12 |  | Creation of Target Vnet |  | Completed | C,I | R,A | I | I | C | Depending on Landing Zone Creation
2026-01-17 | 2026-02-20 |  | 2026-01-28 | 2026-01-28 |  | Creation of Target IP |  | Completed | R,A | I | I |  | C
2026-01-17 | 2026-02-20 |  | 2026-01-20 | 2026-01-21 |  | Create the Isolated Vnet for testing |  | Completed | C,I | R,A | I | I | C | KPMG team will be dependent on FH to create vNets
2026-01-17 | 2026-02-20 |  | 2025-11-12 | 2025-11-12 |  | Provision application/web/DB subnets |  | Completed | C,I | R,A | I | I | C | Depending on Landing Zone Creation
2026-01-17 | 2026-02-20 |  | 2025-11-12 | 2025-11-12 |  | Creation of application gateway |  | Completed | C,I | R,A | I | I | C | Depending on Landing Zone Creation
2026-01-17 | 2026-02-20 |  | 2026-01-28 | 2026-01-28 |  | Provision the Azure Key Vault |  | Completed | R,A | I | I | C,I | C,I
2026-01-17 | 2026-02-20 |  | 2026-01-28 | 2026-01-28 |  | Provision the Azure Recovery Services Vault and configure backup policies for the application |  | Completed | R,A | C,I | I | I | I
2026-02-20 | 2026-02-23 | -16 | 2025-12-19 | 2026-01-16 |  | Migration Runbook - Review & Approval(prod) |  | Completed
2026-02-20 | 2026-02-23 |  | 2025-12-19 | 2025-12-19 |  | Create the Migration Runbook |  | Completed | R,A | I | I | I | C
2026-02-20 | 2026-02-23 |  | 2025-12-19 | 2026-01-16 |  | Get the Migration runbook reviewed & Signoff |  | Completed | A | R | I | I | C,I | KPMG is dependent on the application team and FHA to provide signoff
2026-02-20 | 2026-02-23 | -16 |  |  |  | Notify MS to Initiate the Replication of servers in Azure Migrate |  | Yet-to-start
2026-02-20 | 2026-02-21 |  |  |  |  | Select servers for replication in Azure Migrate. |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-22 | 2026-02-23 |  |  |  |  | Configure replication settings (target region, resource group,VNet,Avalialblity Zone,Vm Size etc). |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-22 | 2026-02-23 |  |  |  |  | Start initial replication to Azure. |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-22 | 2026-02-23 |  |  |  |  | Monitor replication until status is Healthy. |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-24 | 2026-02-27 | -12 |  |  |  | Firewall Opening Request, Local User Account & Server Restart Request |  | Yet-to-start
2026-02-24 | 2026-02-25 |  |  |  |  | Send Request to PHSA to create the Local User account & Restart the server |  | Yet-to-start | R,A | I | I | I | I
2026-02-25 | 2026-02-26 |  |  |  |  | Send Request to PHSA to open the required firewall ports |  | Yet-to-start | C | A | R | I | I | KPMG is dependent on PHSA and FH
2026-02-26 | 2026-02-27 |  |  |  |  | Create Local User Account |  | Yet-to-start | C | A | R |  | I | KPMG is dependent on PHSA and FH
2026-02-25 | 2026-02-27 |  |  |  |  | Restart Servers |  | Yet-to-start | C | A | R |  | I | KPMG is dependent on PHSA and FH
2026-03-04 | 2026-03-06 | -7 |  |  |  | Test-Migration execution of Prod in Isolated Network |  | Yet-to-start
Migration bridge will be live on Teams during the test migration -- relevant team members must join - All the below activities will be performed during the call
2026-03-04 | 2026-03-06 |  |  |  |  | Initiate test Migration for replicated servers |  | Yet-to-start | A | I | I | I | R | KPMG is dependent on Microsoft team
2026-03-04 | 2026-03-06 |  |  |  |  | Choose the isolated virtual network for test migration |  | Yet-to-start | A | I | I | I | R | KPMG is dependent on Microsoft team
2026-03-04 | 2026-03-06 |  |  |  |  | Montior the test migration Job and validate the test VM created with test-servername,drives and nic validation |  | Yet-to-start | A | I | I | I | R | KPMG is dependent on Microsoft team
2026-03-06 | 2026-03-09 | -6 |  |  |  | VM smoke test (Infra-Level) |  | Yet-to-start
2026-03-06 | 2026-03-06 |  | 2025-11-12 | 2025-11-12 |  | Configure Bastion Host to provide access to Vms. |  | Completed | I | R,A | I | I | C,I | KPMG team will be dependent on Landing Zone Creation
2026-03-06 | 2026-03-06 |  |  |  |  | Grant the requested application team access to Azure VMs through Bastion and add them to respective groups on VM | 10 | Yet-to-start | C,I | R,A |  | I | C,I | kPMG is dependent on FH
2026-03-06 | 2026-03-06 |  |  |  |  | Validatethe server is up & running, VM boot diagnostics and IP attached, Check the performance of the server. | 10 | Yet-to-start | R,A | I | I | I | C,I
2026-03-06 | 2026-03-06 |  |  |  |  | Perform Infra level test on migrated VMs -Follow checks from Smoke Test Tab | 20 | Yet-to-start | R,A | I | I | I | C,I | KPMG is dependent on PHSA to shut down on-prem servers
2026-03-09 | 2026-03-09 |  |  |  |  | Document test results (smoke test tab activities will be documented) | 20 | Yet-to-start | R,A | I | I | I | C,I
2026-03-09 | 2026-03-09 |  |  |  |  | Delete test VM after validation. | 10 | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-03-09 | 2026-03-09 |  |  |  |  | Confirm replication remains intact for final migration. | 10 | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-03-09 | 2026-03-11 | -4 |  |  |  | (Go-NoGo) Approval |  | Yet-to-start
2026-03-09 | 2026-03-11 |  |  |  |  | Present the findings from the post-migration phase. This should cover: > Overview of the migration process. > Testing results and whether the success criteria were met. > Issues encountered and their resolution. > User and stakeholder feedback. > Backup and rollback plan status. |  | Yet-to-start | C,I | R,A | I | C | I | KPMG is dependent on FH
2026-03-11 | 2026-03-12 | -3 |  |  |  | Notify users/app team for downtime |  | Yet-to-start
2026-03-11 | 2026-03-12 |  |  |  |  | Send out a formal communication regarding the cutover and the unavailability of the application during the timeframe. |  | Yet-to-start | R,A | I |  | C,I | I
2026-03-12 | 2026-03-16 | -3 |  |  |  | Validate the Replication status is healthy and ensure there are no critical errors prior to the day before migration |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-03-17 | 2026-03-17 | 0 |  |  |  | Prod Cutover and post migration tasks |  | Yet-to-start
2026-03-17 | 2026-03-17 |  |  |  |  | Refer to activites in "T-Zero Cutover Activities" tab |  | Yet-to-start |  |  |  |  | R | KPMG is dependent on Microsoft team
2026-03-17 | 2026-03-17 |  |  |  |  | Configure Backup Policies & attach VMs to the backup Policies & Connet to azure monitor if required | 30 | Yet-to-start | C,A | R |  | I | R | KPMG is dependent on Microsoft team and FH
2026-03-17 | 2026-03-17 |  |  |  |  | Replace the NIC on the migrated VM with the exsiting original static IP by removing the NIC that was automatically created during migration | 30 | Yet-to-start | C,A | I |  | I | R | KPMG is dependent on Microsoft team
2026-03-17 | 2026-03-17 |  |  |  |  | Delete the Vmware Tools and any other softwares that are not required. | 15 | Yet-to-start | R | C,I | I | I | R,A | KPMG is dependent on Microsoft team
2026-03-17 | 2026-03-17 |  |  |  |  | Verify the integrity and completeness of data migrated to Azure | 15 | Yet-to-start | R | C,I | I | R | R,A | KPMG is dependent on Microsoft team
2026-03-17 | 2026-03-17 |  |  |  |  | After migration, Domain Admin or Local Admin logs in to migrated Azure servers to validate the authentication of the credntials | 30 | Yet-to-start | C,I | C,I | R,A | R | C,I | KPMG is dependent on PHSA and app team
2026-03-17 | 2026-03-17 |  |  |  |  | Perform Infralevel testing once vm created using Local admin account |  | Yet-to-start | R,A | I | I | I | C,I
2026-03-17 | 2026-03-17 |  |  |  |  | Modify DNS entry for the Azure Vms with their private ip (if required) | 30 | Yet-to-start | C,I | C,I | R,A | I | C,I | KPMG is dependent on PHSA
2026-03-17 | 2026-03-17 |  |  |  |  | Join the VMs to Domain | 30 | Yet-to-start | C,I | C,I | R,A | I | I | KPMG is dependent on PHSA
2026-03-17 | 2026-03-17 |  |  |  |  | Verify the ports and firewall rule on NSG for the Azure migrated DB and Web server | 15 | Yet-to-start | R,A | I | I |  | C,I
2026-03-17 | 2026-03-17 |  |  |  |  | Update integration configuration to point to the new cloud application | 20 | Yet-to-start | C,I | A | I | R | C,I | KPMG is dependent on FH and app team
2026-03-17 | 2026-03-17 |  |  |  |  | Ensure user have been granted access to the newly migrated applications | 10 | Yet-to-start | I | A | C,I | R | I | KPMG is dependent on FH and app team
2026-03-17 | 2026-03-17 |  |  |  |  | Add the vm to to backendpool of any loadbalancer if required,Associate NSG,ASG |  | Yet-to-start | R,A | R |  | I | C,I | KPMG is dependent on FH
2026-03-17 | 2026-03-17 |  |  |  |  | Verify access to the vendor/application team |  | Yet-to-start | C | C | I | R,A | I | KPMG is dependent on app team |  | The application team will be deploying the application and they will login into the VM via Bastion using their domain ID
2026-03-17 | 2026-03-17 |  |  |  |  | If any, reconfigure the Connection strings, integrations to point to the new environment. This might involve updating API endpoints, re-authenticating, or changing configurations. |  | Yet-to-start | C,I | C,I | I | R,A | I | KPMG is dependent on app team
2026-03-17 | 2026-03-17 |  |  |  |  | Conduct end-to-end testing of each integration to verify they are working as expected. |  | Yet-to-start | C,I | C,I | I | R,A | I | KPMG is dependent on app team
2026-03-17 | 2026-03-17 |  |  |  |  | Ensure UAT test cases are created upfront to perform the testing |  | Yet-to-start | C,I | C,I | I | R,A | I | KPMG is dependent on app team
2026-03-17 | 2026-03-17 |  |  |  |  | Execute test cases and document results. |  | Yet-to-start | C,I | C,I | I | R,A | I | KPMG is dependent on app team
2026-03-17 | 2026-03-17 |  |  |  |  | Document any issues or deviations found during the testing process |  | Yet-to-start | C,I | C,I | I | R,A | I | KPMG is dependent on app team
2026-03-17 | 2026-03-17 |  |  |  |  | Request Partial Sign off from app owners (One week lead time to validate the performance testing to provide the complete sign off)
2026-03-17 | 2026-03-17
2026-03-17 | 2026-03-24 | 5 |  |  |  | Performance & Application Stability testing by application team |  | Yet-to-start
2026-03-17 | 2026-03-24 |  |  |  |  | One week lead time to montior the performance & Stability of the application by app owners |  | Yet-to-start | C,I | C,I | I | R,A | I | KPMG is dependent on app team
2026-03-17 | 2026-03-24 | 5 |  |  |  | User Acceptance Prod Env & Notify Stakeholders of Successful Migration |  | Yet-to-start
2026-03-17 | 2026-03-24 |  |  |  |  | Get the UAT signoff & Communicate all the stakeholders about the successful migration. |  | Yet-to-start | R,A | I | I | I | I
2026-03-25 | 2026-03-25 | 6 |  |  |  | Stop replication in Azure Migrate to finalize migration only after we receive signoff by application team | 10 | Yet-to-start | C,I | I |  |  | R,A | KPMG is dependent on Microsoft team
2026-03-25 | 2026-03-26 | 7 |  |  |  | Lesson Learned |  | Yet-to-start
2026-03-25 | 2026-03-26 |  |  |  |  | Facilitate a structured discussion to identify what went well, what didn’t go well, and areas for improvement. |  | Yet-to-start | R,A | I | I | C | C,I
2026-03-26 | 2026-03-30 | 9 |  |  |  | Knowledge transfer and Transition |  | Yet-to-start
2026-03-26 | 2026-03-30 |  |  |  |  | Formal knowledge transfer sessions with FH cloud support team. |  | Yet-to-start | R,A | R,C | I | I | I
2026-03-26 | 2026-03-30 |  |  |  |  | Formally hand over the system from the migration team to the operational team. Ensure all relevant documentation and access permissions are transferred. |  | Yet-to-start | R,A | C |  | I | A | KPMG is dependent on the operational team to provide signoff
2026-03-30 | 2026-03-31 | 10 |  |  |  | Provide Transition Support |  | Yet-to-start
2026-03-30 | 2026-03-31 |  |  |  |  | Monitor system performance and resolve any issues. |  | Yet-to-start | C | R,A | I | C | I | l
2026-03-30 | 2026-03-31 |  |  |  |  | Updating the documentation based on real-time observations during the hyper care phase |  | Yet-to-start | R,A | I |  | C

## T-Zero Cutover Activities
| T-Zero Cutover Activities | Duration (in Minutes) | Status | KPMG | FHA | PHSA | Applicatiion Team | Microsoft | Dependency
Final Cutover
1 | Notify stakeholders, the application team, and all relevant teams about the migration schedule and unavilablity of servers via email. | 5 | Select | R,A | I | I | C,I | I
2 | Stop any scheduled backups or jobs on the source VM if required for consistency. | 30 | Select | I | I | R,A | R,A | I
3 | Perform final backup of on-premise servers | 30 | Select | I | I | R,A | I | I
4 | Confirm that all necessary application and infrastructure components are configured in Azure - (subnet,keyvault,rsv) | 15 | Select | R,A | C,I | I | I | C,I
5 | Verify replication status is Healthy in Azure Migrate. | 15 | Select | C, I | C,I | I | I | R,A
6 | Validate the target settings like : Target region,RG,VMSIZE,Zone,Target Vnet,Subnet mainly | 15 | Select | C, I | C,I | I | I | R,A
Migration bridge will be live on Teams during the migration -- relevant team members must join - All the below activities will be performed on call
7 | Make sure that atleast one member of on-prem domain admins involved in migration have rdp access to azure migrated VMs (This is required, so that domain admins can login to azure vm post migration and join the machine to domain |  | Select | C | C,I | R,A | I | C
8 | Migration of prod DB (SPDBSRESP001) and Web Servers (SPAPPRESP001,SPAPPRESP002) begins and the On-Prem servers will be shut down during migration with Azure Migrate |  | Select | C,I | C,I | C,I | I | R,A | KPMG is dependent on PHSA to shut down on-prem servers if required
9 | In Azure Migrate, select the replicated server and choose Migrate → Cutover. | 5 | Select | C, I | C,I | I | I | R,A
10 | Select Shutdown source VM option in Azure Migrate | 10 | Select | C, I | C,I | I | I | R,A | KPMG is dependent on PHSA to shut down on-prem servers if required
11 | Start the cutover process; prod DB and Web Servers (SPAPPRESP001,SPAPPRESP002, SPDBSRESP001) Azure will create the VM in the target resource group and virtual network as per the replicated settings defined earlier. | 60 | Select | C, I | C,I | I | I | R,A
12 | Validate the new VM created in Azure Portal | 10 | Select | C, I | C,I | I | I | R,A
13 | Validate Boot status is up and running | 15 | Select | C, I | C,I | I | I | R,A
14 | Replace the NIC on the migrated VM with the exsiting original static IP by removing the NIC that was automatically created during migration | 15 | Select | C, I | C,I | I | I | R,A
15 | Rollback - For Roll back please refer to the Rollback steps section in the below Roll back Section | 30 | Select | C,I | C,I | R,A | I | C,I | KPMG team would be dependent on DNS team
Post-Cutover Activities/Hypercare
16 | Once the vm is migrated successfully and power down, please change the memory to 4 MB. This will prevent the vm to be powered on by accident. | 30 | Select | I | R,A
17 | Post-migration on vCenter, the vCenter administrators should rename the server display name extenstion to .amig and uncheck the NIC. This step is required immediately after migration; otherwise, HARDNS or DRS may automatically initiate a power-on | 30 | Select | I | R,A
18 | Configure Backup Policies & attach VMs to the backup Policies & Connet to azure monitor if required | 30 | Select | C,A | R |  | I | R
19 | Delete the Vmware Tools post migration | 15 | Select | R | C,I | I | I | R,A | KPMG is dependent on Microsoft
20 | Verify the integrity and completeness of data migrated to Azure | 15 | Select | R | C,I | I | R | R,A | KPMG is dependent on Microsoft
21 | After migration, Domain Admin or Local Admin logs in to migrated Azure servers to validate the authentication of the credntials | 30 | Select | C,I | C,I | R,A | R | C,I | KPMG is dependent on PHSA and application team
22 | Perform Infralevel testing once vm created using Local admin account |  | Select | R,A | I | I | I | C,I
23 | Modify DNS entry for the Azure Vms with their private ip (if required) | 30 | Select | C,I | C,I | R,A | I | C,I | KPMG is dependent on PHSA
24 | Join the VMs to Domain | 30 | Select | C,I | C,I | R,A | I | I | KPMG is dependent on PHSA
25 | Verify the ports and firewall rule on NSG for the Azure migrated DB and Web server | 15 | Select | R,A | I | I |  | C,I
26 | Update the integration configurations (endpoints, connection strings ) to reference the new cloud app and to validate the connectivity. | 20 | Select | C,I | A | I | R | C,I
27 | Ensure user have been granted access to the newly migrated applications | 10 | Select | I | A | C,I | R | I
28 | Add the vm to to backendpool of any loadbalancer if required,Associate NSG,ASG |  | Select | R,A | R |  | I | C,I
29 | Verify access to the vendor/application team |  | Select | C | C | I | R,A | I | KPMG is dependent on Application Team
30 | If any, reconfigure the Connection strings, integrations to point to the new environment. This might involve updating API endpoints, re-authenticating, or changing configurations. |  | Select | C,I | C,I | I | R,A | I | KPMG is dependent on Application Team
31 | Conduct end-to-end testing of each integration to verify they are working as expected. |  | Select | C,I | C,I | I | R,A | I | KPMG is dependent on Application Team
32 | Ensure UAT test cases are created upfront to perform the testing |  | Select | C,I | C,I | I | R,A | I | KPMG is dependent on Application Team
33 | Execute test cases and document results. |  | Select | C,I | C,I | I | R,A | I | KPMG is dependent on Application Team
34 | Document any issues or deviations found during the testing process |  | Select | C,I | C,I | I | R,A | I | KPMG is dependent on Application Team
35 | Request Partial Sign off from app owners (One week lead time to validate the performance testing to provide the complete sign off) |  | Select | R,A | I | I |  | C,I
36 | One week lead time to montior the performance & Stability of the application by app owners |  | Select | R,A | I | I | I | I
37 | For Next one week Monitor the system to track application health & Verify application uptime and responsiveness Check logs for errors or warnings Confirm monitoring alerts are configured and active |  | Select | R,A | I | I | I | C,I
38 | Get the UAT sign off & Notify stakeholders of successful migration |  | Select | R,A | C,I | I | C,I | C,I
39 | Optimize VM sizes and Azure resources if applicable based on performance data Review CPU, memory, and disk utilization Adjust VM sizes as needed Validate cost optimization recommendations |  | Select | C,I | C,I | I | C,I | R,A | Microsoft will perform the changes SKU changes based on the inputs from PHSA/FH
40 | Update all relevant documentation to reflect the new environment and any changes made during the migration Update architecture diagrams Revise operational runbooks and SOPs Document resource names, IPs, and configurations |  | Select | R,A | C,I | I | I | C,I
41 | Post Migration review and lessons learned Conduct review meeting with project team Capture issues, successes, and improvement areas Share findings with stakeholders |  | Select | R,A | I | C,I | C | C,I | KPMG needs to work with the PHSA.FHA and application team to document lessons learnt
42 | Start process of decommissioning old systems Validate no dependencies remain on old systems Schedule decommissioning tasks Update asset inventory and CMDB |  | Select | I | R,A | C,I | C |  | KPMG is dependent on FHA to request for decommissioning old systems
Rollback Steps
1 | Delete or update the DNS record pointing to the Azure-hosted application & Restore DNS to point back to the on-premise application servers. |  | Select | C,I | I | R,A | I | I
2 | Power on the application and database servers that were shut down during migration Verify network connectivity and services. |  | Select | C | I | R,A | I | I
3 | Perform Smoke Test on the restored Application |  | Select | C | I | I | R,A | I
4 | If required, restore VM snapshots. Restore database backup to ensure data consistency. |  | Select | C | C,I | R,A | C,I | I
5 | Send email to application, PHSA, and stakeholders on completion of change |  | Select | R,A | C,I | I | I | I
6 | Stop or deallocate Azure Web and DB servers to avoid unnecessary costs. Confirm no traffic is routed to Azure. |  | Select | R | C,I | I | I | R,A
7 | Ensure on-prem monitoring and backup jobs are re-enabled. |  | Select | C,I | C,I | R,A | C,I | I
8 | Send formal email to all users: Application is restored and available. Notify application team, PHSA, and stakeholders about rollback completion and reason for migration failure. |  | Select | R,A | C,I | I | I

## Smoke Test
Smoke Test Checks
|  | Status | KPMG | FHA | PHSA | App Team | MS | Applicatiion Team | Dependency
Checks
1 | Ensures that login is possible with both the local administrator account and the domain (SA) after migration. |  | R,A | C,I | C,I |  | R
2 | Verify migrated VMs are powered on and accessible via RDP/SSH. Check IP addresses, DNS resolution, and network connectivity within the VNet. Confirm NSG and firewall rules allow expected traffic. Check CPU, memory, and disk utilization on migrated VMs. Validate disk mounts and storage paths are correct. |  | R,A | I | C,I | I | R,C
3 | Verify port connectivity for requested On-Prem Servers and azure migrated servers with Test-NetConnection <ComputerIp> -Port <port> or Telnet. If ports are not opened, inform PHSA via email, Check critical workflows (e.g., form submission, navigation). |  | R,A | C,I | R | I | C,I
4 | Verify that the requested application team users have been added to the machine with the intended access permissions within computer users and groups, if not, add those users and groups to administartor group |  | C,I | R,A | C,I | C,I | C,I
5 | Check the azure bastion access and resource group access for the above requested users from application team, if not request PHSA to add those users with reader access |  | R,A | R | C,I | I | C,I
6 | Application Smoke Testing needs to be performed by App team |  | C,I | C,I | I | R,A | C,I

## Target details
Server Name | Application/Services running | Hostname | FQDN | Target Subscription Name | Target Resource Group | Target Vnet | Target Subnet | Register with SQL IaaS extension(Y/N) | Windows Server license(Y/N) | Availability Option | Automatically repair replication(Y/N) | Availability Zone(1/2/3/None)) | Target IP | Environment | Test Vnet | Test Subnet | Azure Region | Backup Policy | Recovery Service Vault | Storage Account | OS Disk Name(If we have multiple disks) | Recommended SKU Size | Remarks
SDAPPRESP001 | Book a Break | SDAPPRESP001 | sdappresp001.fraserhealth.org | fraserhealth-tst-prv-nonclinical-01 | fraserhealth-cc-dev-rg-bookabreak-01 | fraserhealth-cc-tst-prv-nonclinical-vnet-01 | AppSubnet-01-Internet | No | Yes | TBD | Yes | TBD |  | Dev | fraserhealth-cc-tst-prv-nonclinical-migration-nonroute-vnet-01 | migration-snet-01 | canadacentral | fraserhealth-cc-dev-backup-policy-bookabreak-01 |  |  |  | Standard_B2as_v2
SDDBSRESP001 | Book a Break | SDDBSRESP001 | sddbsresp001.fraserhealth.org | fraserhealth-tst-prv-nonclinical-01 | fraserhealth-cc-dev-rg-bookabreak-01 | fraserhealth-cc-tst-prv-nonclinical-vnet-01 | DataSubnet-01 | TBD | Yes | TBD | Yes | TBD |  | Dev | fraserhealth-cc-tst-prv-nonclinical-migration-nonroute-vnet-01 | migration-snet-01 | canadacentral | fraserhealth-cc-dev-backup-policy-bookabreak-01 | fh-cc-dev-rsv-bab-01 |  |  | Standard_B2as_v2

## Responsible Team Members
Responsible Team Members
|  | Availblity | KPMG | FHA | PHSA | Applicatiion Team | Dependency
Team
1 | DNS Team
2 | Domain Admin Group Member
3 | KPMG Migration Team | Yes | seenu.r@fraserhealth.ca tusharnihalani@kpmg.com | Hao.Yan@fraserhealth.ca Mustafa.Mete@fraserhealth.ca
4 | Networking Team
5 | Application Team [Web/DB] |  |  |  |  | Hao.Yan@fraserhealth.ca Mustafa.Mete@fraserhealth.ca
6 | Windows Team
7

## Application-Testing-users
Executive Dashboard - Application Team Access
| Name | Group
1
2
3
4
5
6

## Pre-req (hidden)
Identify Wave 1 applications
Conduct an inventory of all existing applications
Set criteria for selecting pilot applications, such as business impact, technical complexity, dependencies, and user base.
Finalize Pilot App and Signoff
Platform setup and Provision Non-Prod Infras
Establish connectivity between on-premises and Azure using VPN or ExpressRoute (One time task)
Submit request for Azure Subscription creation (if applicable)
Define roles and permissions and assign them to users and groups and Migrate project

## Infra Testing (hidden)
| Infra test | Owner | Status
1 | Pre-Migration Planning and Validation
Confirm that hardware requirements (CPU, memory, storage) meet or exceed those of the source environment.
Verify network configuration, including IP address assignment, subnets, VLANs, and firewall rules within Azure portal.
Ensure all necessary software, middleware, and VM Extenssions are installed and configured on a VM (e.g., web servers, application servers, databases).
2 | Environment Setup Validation
Servers:
Verify server configurations (operating system).
Ensure proper server naming conventions and domain membership.
Check VM (SKU) - Right Sizing
Storage:
Validate storage configurations, including SAN/NAS settings and permissions.
Verify data storage paths and quotas.
Test read/write access to storage resources.
Network:
Test network connectivity between servers and other critical components.
Validate firewall and security group settings.
Check DNS configuration and resolution.
Load Balancers:
Verify load balancer configurations and settings.
Test load balancing policies and failover mechanisms.
3 | Security Configuration Checks
Verify firewall rules and antivirus/antimalware settings.
Ensure appropriate RBAC roles are correctly configured.
Validate encryption and security certificates (SSL/TLS).
4 | Backup and Recovery Testing
Validate backup policies are configured and assigned on VM correctly.
5 | Performance Testing
Servers:
Perform CPU, memory, and disk I/O benchmarks.
Stress test servers to ensure they can handle expected load.
Network:
Measure network latency, bandwidth, and throughput.
Perform load and stress testing on network paths, including between data centers or cloud regions if applicable.
Storage:
Test disk throughput and IOPS performance.
6 | Monitoring and Logging Validation
Ensure monitoring tools and agents are installed and configured.
Validate that key metrics (CPU, memory, disk usage, network traffic) are being monitored.
Check that alerting mechanisms are set up for critical conditions and events.
Verify logging configuration and ensure logs are being collected and stored properly in loganalytics workspace
7 | Compliance and Governance Checks
Ensure all infrastructure components comply with FH regulatory requirements and standards.
Verify audit trails and access logs are correctly configured.
Ensure data protection mechanisms (encryption, masking) are in place.
8 | Post-Migration Validation and Handoff
Conduct a final review with stakeholders to confirm that all infrastructure components are functioning as expected.
Provide documentation of the new environment, including architecture diagrams, configuration settings, and operational procedures.
Handover to operational teams, ensuring they are trained on the new environment and any specific processes or procedures.

## App Testing (hidden)
| Application testing | Owner | Status
1 | Environment Verification
Verify all infrastructure components (servers, storage, network) are correctly set up.
Ensure all necessary services and dependencies (databases, third-party services) are operational.
Confirm that environment variables and configuration settings match those of the source environment.
2 | Data Integrity Checks
Validate that all data has been successfully migrated without loss or corruption.
Confirm data relationships and constraints (e.g., primary keys, foreign keys) are intact.
Compare a subset of data entries from source and destination for accuracy.
3 | Application Access and Permissions
Verify user roles and permissions are correctly configured.
Ensure users can log in and access the application as expected.
Check that secure areas and data protection measures (e.g., encryption) are functioning properly.
4 | Functional Testing
Execute functional tests to validate core application functionalities are working as expected.
Test all critical paths, features, and user workflows.
Run automated regression tests to ensure no unintended changes have occurred.
5 | Performance Testing
Conduct performance tests to ensure the application meets performance requirements.
Analyze response times, throughput, and resource utilization.
Compare performance metrics against benchmarks from the source environment.
6 | Compatibility Testing
Verify that the application is compatible with all intended browsers and devices.
Test the application on different operating systems and hardware configurations.
Check compatibility with any integrated software or APIs.
7 | Security Testing
Conduct security assessments to identify potential vulnerabilities.
Perform penetration testing and vulnerability scanning.
Ensure all security controls are in place and functioning as intended.
8 | Backup and Recovery Verification
Test backup procedures to ensure data can be restored successfully.
9 | User Acceptance Testing (UAT)
Engage end-users to conduct acceptance testing and provide feedback.
Address any issues or concerns raised by users during UAT.
Obtain formal sign-off from stakeholders confirming the application’s readiness.
10 | Logging and Monitoring
Ensure logging mechanisms are correctly set up and operational.
Monitor application logs for any errors or anomalies.
Set up alerts for critical error conditions.

## Migrate SQL DB (hidden)
Azure Database Migration Service (DMS) to migrate your SQL DB to Azure
| Activity | Owner | Status
1 | Preparation and Planning
1.1 | Define the scope and goals: Understand your migration requirements.
1.2 | Inventory existing databases: List all databases that need migration.
1.3 | Assess your environment: Use tools like Data Migration Assistant (DMA) to assess database readiness and compatibility.
1.4 | Choose Azure target: Decide where the database will be hosted in Azure. Options include Azure SQL Database, Azure SQL Managed Instance, or SQL Server on Azure VM.
2 | Create a Migration Project
2.1 | Create a DMS instance:
2.1.1 | 1. Go to "Create a resource" > "Integration" > "Azure Database Migration Service".
2.1.2 | 2. Fill in the required details like subscription, resource group, and instance name.
2.1.3 | 3. Configure virtual network settings to allow DMS to communicate with the source and target databases.
2.1.4 | 4. Create the service.
2.2 | Create a new migration project:
2.2.1 | 1. In your DMS instance, select "New Migration Project".
2.2.2 | 2. Name your project.
2.2.3 | 3. Select the source and target server types.
2.2.4 | 4. Choose the type of migration: Online or Offline.
3 | Prepare the Source and Target Databases
3.1 | Backup your data: Ensure that you have a recent backup of the source database.
3.2 | Configure source environment:
3.3 | Make sure the source database is accessible.
3.4 | Minimize active workloads during the migration, especially for online migrations.
3.5 | Configure target environment:
3.6 | Create the target database schema if needed.
3.7 | Ensure the target database is correctly configured and ready to receive data.
3.8 | Apply necessary security and firewall rules to allow DMS to access the target.
4 | Set up Migration Activity
4.1 | Perform initial migration steps:
4.1.1 | 1. Add source details: Provide the necessary credentials and connection info to connect to your source database.
4.1.2 | 2. Add target details: Provide the necessary credentials and connection info to connect to your target database.
4.1.3 | 3. Map source to target: Identify the databases or tables that you want to migrate.
4.2 | Select objects to migrate:
4.2.1 | Choose the required databases or specific tables, stored procedures, etc.
4.3 | Set up activity:
4.3.1 | Review the migration settings.
4.3.2 | Start the migration.
5 | Monitor and Manage Migration
5.1 | Monitor the migration process:
5.1.1 | Track the progress through the DMS project dashboard in the Azure Portal.
5.1.2 | Address any issues or warnings that arise during the migration.
5.2 | Verify the data:
5.2.1 | Perform a thorough check of the data on the target database to ensure the migration was successful.
5.3 | Final cutover (for online migrations):
5.3.1 | Perform a final synchronization to make sure all changes from the source are applied.
5.3.2 | Redirect applications to point to the new Azure database.
6 | Post-Migration
6.1 | Operational Validation:
6.1.1 | Validate application performance and functionality.
6.1.2 | Ensure backups are configured for the new Azure-hosted database.
6.2 | Optimize Post-Migration:
6.2.1 | Fine-tune the database performance.
6.2.2 | Look at any necessary indexing or optimization work.
Azure migrate for SQL DB
1 | Planning and Assessment:
1.1 | Discovery: Use the Azure Migrate service to discover the on-premises SQL instances and databases. Install the Azure Migrate appliance to help with the discovery process.
1.2 | Assessment: Evaluate the readiness and compatibility of your SQL databases for migration to Azure SQL Database, Azure SQL Managed Instance, or SQL Server on Azure VMs. The assessment will provide details on any required changes, performance metrics, and potential cost.
2 | Preparation:
2.1 | Choose the Right Service: Decide whether you want to migrate to Azure SQL Database, Azure SQL Managed Instance, or SQL Server on Azure VMs based on your assessment results.
2.2 | Size and Configurations: Determine the appropriate size and configuration for your Azure SQL target based on the performance metrics obtained during the assessment.
3 | Setting Up the Azure Environment:
3.1 | Azure Subscription: Ensure you have an active Azure subscription.
3.2 | Resource Group: Create a resource group in Azure to manage your resources.
3.3 | Networking: Set up networking resources such as virtual networks, subnets, and network security groups if required.
4 | Migration Tools Setup:
4.1 | Azure Database Migration Service (DMS):
4.2 | Deploy an Azure Database Migration Service instance in Azure.
4.3 | Create a new migration project in the DMS and specify your source and target details.
5 | Data Migration:
5.1 | Offline Migration: If downtime is acceptable, you can use the offline migration method where databases can be copied directly to the Azure target. This is generally faster but requires planned downtime.
5.2 | Online Migration: For minimal downtime, use online migration which allows you to continually replicate changes from your source SQL database to the target until you're ready to switchover with minimal downtime.
6 | Migration Execution:
6.1 | Backup and Restore: For some scenarios, taking a full backup of the on-premises database and restoring it to Azure SQL might be a viable option.
6.2 | Data Migration Assistant (DMA) and DMS: For complex migrations, use the Data Migration Assistant to identify compatibility issues and then use the Database Migration Service to migrate your databases.
7 | Testing and Validation:
7.1 | Post-Migration Testing: Once the migration is complete, thoroughly test your applications to ensure they function as expected with the Azure SQL database.
7.2 | Validation: Validate the data integrity and performance of the Azure SQL database after migration.
8 | Cutover and Decommissioning:
8.1 | Cutover: When you are satisfied with the testing and validation, schedule a final cutover to switch production workloads to the Azure SQL database.
8.2 | Decommissioning: Decommission the on-premises SQL Servers if they are no longer needed after migration.
9 | Post-Migration Optimization:
9.1 | Performance Tuning: Monitor and optimize the performance of your Azure SQL environment. Adjust resources as needed.
9.2 | Backup and Recovery: Set up proper backup and recovery procedures for your new Azure SQL databases.
9.3 | Security: Ensure that security policies and compliance requirements are met for your Azure SQL databases.

## Migrate Files systems (hidden)
File system migration using Azure File Sync
| Activities | Owner | Status
1 | Deploy the Storage Sync Service
1.1 | Create Storage Sync Service:
1.2 | Sign in to the Azure portal.
1.3 | Navigate to Create a resource > Compute > Storage Sync Service.
1.4 | Fill in the Resource group, Subscription, and Name.
1.5 | Click on Review+Create > Create.
2 | Prepare Windows Server to Use with Azure File Sync
2.1 | Install the Azure File Sync Agent:
2.2 | Download the Azure File Sync agent.
2.3 | Install the agent on your Windows Server.
2.4 | Restart the server if necessary.
2.5 | Register Windows Server:
2.6 | Open the Azure File Sync utility on your server.
2.7 | Go through the registration process, which involves logging in to Azure and selecting the Storage Sync Service created earlier.
3 | Create a Sync Group and Add Server Endpoints
3.1 | Create a Sync Group:
3.2 | In the Azure portal, navigate to your Storage Sync Service.
3.3 | Click on Sync groups > Add Sync Group.
3.4 | Fill in the Name and select the Storage Account and Azure File Share created earlier.
3.5 | Click Create.
3.6 | Add Server Endpoint:
3.7 | After creating the sync group, click on it.
3.8 | Click on Add server endpoint.
3.9 | Select the Registered server (your on-prem server).
4 | Enter the Path on the on-premises server that you want to sync.
4 | Set Up and Monitor Sync
4.1 | Initial Sync:
4.2 | Once the server endpoint is added, the initial sync will begin. This might take a while depending on the amount of data.
4.3 | Monitor the sync status in the Azure portal.
4.4 | Cloud Tiering (Optional):
4.5 | If you have limited space on your on-premises server, enable Cloud Tiering to store frequently accessed files locally and store the rest in the Azure file share.
5 | Verify Synchronization
5.1 | Check Synchronization:
5.2 | Verify that files are being synchronized between the on-premises server and the Azure file share.
5.3 | Ensure there are no errors or issues reported in the sync process.
6 | Cut Over to Azure File Share (Optional)
6.1 | Final Steps:
6.2 | Once the initial sync is complete, you may optionally cut over fully to the Azure file share.
6.3 | Change any applications or services to use the Azure file share instead of the local file server paths.
6.4 | Decommission the local file shares if no longer needed.
Migrate On-Premises File Servers to Azure using Azure Migrate
1 | Set Up Azure Migrate
1.1 | Sign in to the Azure portal.
1.2 | Search for Azure Migrate and click on it.
1.3 | Click on Create project.
1.4 | Fill in the Project details, such as Subscription, Resource Group, and Project Name.
1.5 | Click Create.
2 | Assess Your File Server
2.1 | Add Tools to Assess and Migrate:
2.1.1 | In your Azure Migrate project, click on Discover.
2.1.2 | Select Servers and then Discover.
2.1.3 | Under Discovery and assessment tool, select Azure Migrate: Server Assessment.
2.1.4 | Click Add Tool.
2.2 | Prepare for Discovery:
2.2.1 | Download the Azure Migrate appliance setup.
2.2.2 | Deploy the Azure Migrate appliance on a VM or physical server in your on-premises environment.
2.2.3 | Configure and connect the appliance to Azure Migrate. This involves setting up an appliance configuration manager that guides you through connecting to Azure and performing the initial discovery.
2.2.3.4 | Perform server discovery and assessment.
3 | Create an Assessment
3.1 | Once the discovery is complete, navigate to Assess on the Azure Migrate portal.
3.2 | Create a new assessment for your file servers.
3.3 | Review the assessment reports to understand the readiness, estimated cost, and performance metrics for migrating your file servers to Azure.
4 | Plan for Migration
4.1 | Under Migrate in your Azure Migrate project, click on Servers.
4.2 | Choose the Azure Migrate: Server Migration tool to add it to your project.
5 | Set Up and Start Replication
5.1 | Prepare On-Premises Environment for Replication:
5.1.1 | Download and install the Azure Site Recovery Unified Setup on your on-premises server (or on a dedicated replication server).
5.1.2 | Register the on-premises server with the Azure Site Recovery vault, which is part of the Azure Migrate: Server Migration tool.
5.2 | Configure Replication:
5.2.1 | In the Azure portal, navigate to your Azure Migrate project and find the Replicate section under Migrate.
5.2.2 | Specify the prerequisites, which include the source settings, target settings, and replication settings.
5.2.3 | Configure a replication policy and enable replication for your file servers.
6 | Perform and Monitor Replication
6.1 | Once replication is enabled, an initial replication of your file servers to Azure will occur.
6.2 | Monitor the replication process through the Azure Migrate portal to ensure no issues arise.
7 | Test and Cutover
7.1 | Test the Migration:
7.1.1 | Before finalizing the migration, perform a test migration to validate that files, permissions, and configurations are correctly replicated.
7.1.2 | In the Azure Migrate: Server Migration tool, choose Test Migration for the replicated servers. This creates a test VM in an isolated Azure network.
7.1.3 | Validate the test migration, including application functionality and data integrity.
7.2 | Perform Final Migration (Cutover):
7.2.1 | Once testing is successful, perform the final migration (cutover).
7.2.2 | In the Azure Migrate portal, choose Migrate for the replicated servers to complete the migration process.
7.2.3 | Stop the replication and shut down the on-premises file servers to ensure a successful cutover and avoid conflicts.
Migrate On-Premises File Servers to Azure Using Azure Data Box
1 | Order Azure Data Box
1.1 | Sign in to the Azure portal.
1.2 | Navigate to All services > Storage, and select Data Box.
1.3 | Click on Order Data Box and choose the appropriate Data Box (Data Box, Data Box Disk, or Data Box Heavy based on your data size).
1.4 | Fill in the necessary details like Subscription, Resource Group, and Destination Storage Account.
1.5 | Provide shipping details and confirm your order.
2 | Receive and Set Up the Data Box
2.1 | Delivery and Preparation:
2.1.1 | Once the Data Box arrives, follow the instructions provided to inspect and power up the device.
2.1.2 | Connect the Data Box to your local network.
2.2 | Configuration:
2.2.1 | Download and install the Data Box Client software from the Microsoft website.
2.2.2 | Use the Data Box Client to connect to the Data Box device.
2.2.3 | Set up your Data Box by following the setup wizard, which includes configuring network settings and setting up a local secure connection.
3 | Copy Data to Data Box
3.1 | Once the Data Box is connected and configured, use standard file copy tools (like Robocopy, AzCopy, or any other data copy method) to transfer your on-premises file server data to the Data Box.
3.2 | Ensure to validate the data copy operations and check logs for any errors.
4 | Prepare Data Box for Shipment Back to Azure
4.1 | After the data copy process completes, follow the provided instructions to disconnect and securely prepare the Data Box for return.
4.2 | Use the shipping labels provided with the Data Box to send it back to the Azure data center.
5 | Azure Imports Data from Data Box to Storage Account
5.1 | Once Azure Data Box reaches the data center, Microsoft will handle the data import process to your specified Azure Storage account.
5.2 | Monitor the import status in the Azure portal under the Data Box service.
6 | Post-Import Activities
6.1 | Verify Data:
6.1.1 | After data import is complete, verify that all data appears correctly in your Azure Storage account.
6.1.2 | Check for data integrity and perform any necessary data validation steps.
6.2 | Set Up Azure File Sync (Optional):
6.2.1 | If you'd like continuous synchronization between your on-premises file server and Azure, consider setting up Azure File Sync as described in the previous response.

## Migrating VMs detailed steps (hidden)
Azure Migrate:Migrating VMs
| Activity | Owner | Status
1.0.1 | Phase-1-Prerequisites
1.0.1.1 | Before you can migrate a source VM to Azure, you must configure the migration environment on your on-premises data center and on Azure. Ensure to get the performace benchmark of the application.
1.0.1.2 | 1.Enable Azure Migrate services
1.0.1.3 | 2.Installing the Migrate Connector
1.0.1.4 | 3.Adding a target subscription
1.0.1.5 | 4.Configuring permissions for a Shared vnet
1.0.1.6 | 5.Configuring permissions on target subscription service account
1.0.2 | Phase2-Source Setup
1.0.2.1 | The first phase of migration is to onboard the source VM(You can have up to 200 migrations in progress, meaning migrations that you have onboarded, not counting migrations in the Finalize phase.)
1.0.2.2 | To onboard a source VM follow the below steps:
1.0.2.3 | 1.Open the Azure Migrate page in the Azure console:Go to the Azure Migrate page
1.0.2.4 | 2.Select the Sources tab.
1.0.2.5 | 3.From the drop-down list, select the source corresponding to the on-prem data center where you installed the Migrate Connector. The data center is referred to as a migration source.
1.0.2.6 | Below the dropdown you see the Source status of the data center as:
1.0.2.7 | Active: The source is active and connected to Azure Migrate.
1.0.2.8 | Offline: The source is unavailable.
1.0.2.9 | Pending: The source is in the process of being connected and verified.
Note: If you do not see any entries in the drop-down list, it means you have not yet installed the Migrate Connector in an on-premises data center
1.0.2.10 | A table appears showing the source VMs in the data center available for migration. Select one or more source VMs.
Note: The VM Power Status column shows the status as Suspended, On, or Off. You can migrate a VM with any of these statuses.
1.0.2.11 | 5.Click Add Migration.
1.0.2.12 | 6.Confirm that you want to create the migration.
After you create a migration, the Replication status column for a VM displays one of the following:
Pending: VM is in the process of being onboarded.
Ready: VM is onboarded but not yet replicating.
7.You can now start replication of the VMs as described in the next section
1.0.3 | Phase 3-Migration
1.0.3.1 | After onboarding a source VM, start replicating the disk data from the source VM to Azure. This process takes place in the background with no disruption to the on-prem workload.
1.0.3.1 | Data replication is comprised of two steps:
1.0.3.2 | First replication step: Azure Migrate creates the initial VM snapshot of the source VM data disks and replicates the snapshot data to Azure. Depending on the amount of disk data on the source VM, the first replication can take minutes or hours to complete.
1.0.3.3 | The Replication status column of a VM on the first replication step displays the First sync status followed by the appropriate sub-step.
1.0.3.4 | Incremental replication step: Following a successful first replication step, incremental replication steps occur at set time intervals (every two hours by default). In each step, a new snapshot is created for each data disk. Only data updates that occurred after the previous step are replicated to Azure using the Change Block Tracking (CBT) mechanism.
1.0.3.5 | The Replication status column of a VM on an incremental replication step displays the Active status followed by the appropriate sub-step.
1.0.3.6 | To initiate replication of a source VM:
1.0.3.7 | Open the Azure Migrate page in the Azure console:
1.0.3.8 | Go to the Azure Migrate page
1.0.3.9 | Select the Migrations tab.
1.0.3.10 | A table appears showing the source VMs in the data center that you have onboarded. You can start replication on any VM with the replication status Ready.
Select one or more source VMs.
1.0.3.11 | Click Migration > Start Replication.
1.0.3.12 | pause replication:
1.0.3.13 | At any time, you can pause replication for a VM. When you pause a VM, its Replication status changes to Paused.
1.0.3.14 | Open the Azure Migrate page in the Azure console:
1.0.3.15 | Go to the Azure Migrate page
1.0.3.16 | Select the Migrations tab.
1.0.3.17 | A table of available source VMs appears.
1.0.3.18 | Select one or more VMs.
1.0.3.19 | Select Pause.
1.0.3.20 | To later resume replication, select one ore more VMs and then select Resume.
1.0.3.21 | To set the replication interval:
1.0.3.22 | By default, Azure Migrate performs a replication of the source VM every 2 hours. To change the replication frequency:
1.0.3.23 | Open the Azure Migrate page in the Azure console:
1.0.3.24 | Go to the Azure Migrate page
1.0.3.25 | Select the migration tab
1.0.3.26 | A table of available source VMs appears.
1.0.3.27 | Select the Info panel icon, Info panel file icon, for the VM. A panel opens to let you configure the target.
1.0.3.28 | Note: To set the frequency for multiple VMs, select the VMs and then select the Edit Target Details button. A panel opens to let you configure the selected VMs.
1.0.3.29 | Select the Target Details tab.
1.0.3.30 | In the Replication policy area, set the replication frequency, in seconds.
1.0.3.31 | Select Save.
1.0.4 | Phase 4-Configuring the target for a migrated VM
1.0.4.1 | To configure a target, you perform two main steps:
1.Add a target subscription. The target subscription is the subscription that contains the Azure VM instance used to host the migrated VM.
1.0.4.1 | 2.Configure the Azure VM instance used to host the migrated VM. For both a test and a production environment, configure the target Azure VM instance to specify:
.Azure subscription
Number of CPUs
Amount of memory
Disk size
many other options
1.0.4.2 | To configure a target, you perform two main steps:
1.0.4.3 | 1.To configure the Azure VM target:
1.0.4.4 | If you have not done so already, add the target subscription as shown in Adding a target.
1.0.4.5 | 2.Open the Azure Migrate page in the Azure console:
1.0.4.6 | 3.Go to the Azure Migrate page
1.0.4.7 | 4.Select the Migrations tab.
1.0.4.8 | A table of migrations appears.
1.0.4.9 | 5.Select your desired VM (you can select multiple to edit) and then select the Edit target details button. A panel opens to let you configure the target details for all of your selected VMs.
1.0.4.10 | Set the Target details that define the characteristics of the Azure VM instance used to host the migrated VM.
1.0.4.11 | 6.Select save.
1.0.5 | Phase 5 -Pre-cutover process
1.0.5.1 | In the cut-over phase, you cut over control to your migrated VM running in a Azure VM instance in your production environment on Azure.
1.0.5.2 | 1.If data replication is currently active, meaning the Replication status of the VM is Active (Current cycle: XX%), waits for it to complete.
1.0.5.3 | 2.Shuts down the source VM.
1.0.5.4 | 3.Performs the final data replication. Because replication occurs throughout all migration phases, the amount of data to replicate should not be very large.
1.0.5.5 | 4.Stops replication.
1.0.5.6 | 5.Creates the Azure VM instance from the final replicated data.
1.0.5.7 | The cut-over phase includes a short VM downtime and should take place during a scheduled maintenance window. You must determine the maintenance window during which you can stop the source VM and redirect traffic to the migrated VM running on Azure VM.
Phase 6:Cutover to target sytem
1.0.5.8 | To cut over:Ensure that you have configured the VM target details as shown in Configuring VM target. If the target details were previously configured for test-clone operation, you might want to edit the target details to point to a new target.
1.0.5.9 | Open the Azure Migrate page in the Azure console
1.0.5.10 | Select the Migrations tab.
1.0.5.11 | A table of available source VMs appears. You can cut over any VM that is in the Active (Current cycle: XX%) or Active (idle) state. The Active state means the first replication sync of the VM succeeded and VM data is being incrementally replicated.
1.0.5.12 | Select a source VM.
1.0.5.13 | Select Cut-Over and Test-Clone > Cut Over. Initiating a cut-over on a migrating VM starts the following sequence of actions performed by Azure Migrate:
1.0.5.14 | a.Shuts down the source VM.
1.0.5.15 | b.Performs the final data replication. Because continuous replication occurs throughout all migration phases, the amount of data to replicate should not be very large.
1.0.5.16 | c.Creates the Azure VM instance hosting the migrated VM from the final replicated data.
1.0.5.17 | d.Stops data replication.
To view the cut over history for a VM, select the Info panel icon, Info panel file icon, for that VM.
1.0.5.18 | Phase 7: Validation
Perform validation test on the migrated workload.
1.0.6 | Phase 6:Rollback steps
1.0.6.1 | To rollback from cut over:
1.0.6.2 | Cut over stops the original source VM in your on-premises data center, so you must start it and redirect traffic back to the source VM.
1.0.6.3 | If necessary, copy new data created on the Azure VM instance so that you can write it to the source VM.
1.0.6.4 | Optionally delete or shutdown the Azure VM instance running the migrated VM.
1.0.6.5 | Resume replication on the source VM as shown above. Replication resumes from the last snapshot taken.
1.0.6.6 | Retry cut over.

## Azure migrate VM migration Acti (hidden)
Azure Migrate: Migrating VMs
| Activities | Owner | Status
1 | Create Azure Migrate Project: | FH | Completed
| Navigate to Azure Migrate: Go to the Azure portal and search for "Azure Migrate". | FH | Completed
| Create Project: Create a new Azure Migrate project and specify the subscription and resource group. | FH | Completed
| Choose Assessment and Migration Tools: Select the appropriate tools for assessment (e.g., Discovery and Assessment tool) and migration (e.g., Server Migration tool). | FH | Completed
2 | Assess On-Premises Environment: | FH | Completed
| Download and Install Azure Migrate Appliance: Download the Azure Migrate appliance to the on-premises environment. | FH | Completed
| Configure Appliance: Provide Azure Migrate project details and configure the appliance to discover on-premises servers. | FH | Completed
| Discover Machines: Start the discovery process to identify and inventory the VMs in your environment. | FH | Completed
| Run Assessment: Assess the readiness, suitability, and cost implications of migrating the discovered VMs to Azure. | FH | Completed
3 | Review Assessment Findings: | KPMG | Completed
| Suitability Analysis: Review the assessment report for recommendations on which VMs are suitable for migration to Azure. | KPMG | Completed
| Cost Estimation: Check the cost estimates provided for running your VMs in Azure. | KPMG | Completed
| Performance Metrics: Evaluate performance-related metrics to ensure that Azure can meet your VMs' requirements. | KPMG | Completed
4 | Set Up Azure Environment:
Create an Azure Account: If you don't have one, create an Azure account.
Set Up Azure ManagementGroup/Subscription: Ensure you have an active Azure subscription.
Resource Group: Create a new resource group or use an existing one.
5 | Prepare for Migration:
Prepare Network Components: Set up Azure Virtual Network (VNet) and subnets as required. Inaddition deploy and configure NSGs
Prepare Storage Requirements: Ensure adequate Azure storage is available for the migrated VMs.
Configure Identity and Access Management: Set up appropriate permissions and roles in Azure for migration.
Prepare Backup & DR Components: Setup recovery services vault, backup policies and Azure site recovery (if applicable)
Prepare and configure key management solution: Configure keyvaults and vault access policies
6 | Migrate VMs:
Select VMs for Migration: Choose the VMs you want to migrate from the assessment tool.
Replicate VMs: Start replication by configuring replication settings for each of the VMs selected for migration.
Monitor Replication: Monitor the replication process to ensure data is being transferred correctly.
7 | Test Migration:
Perform Test Migrations: Execute test migrations of replicated VMs to validate the migration process.
Validate Functionality: Ensure that VMs work as expected post-migration in the test environment.
8 | Execute Final Migration:
Finalize Migration Plan: Plan downtime and final cutover activities.
Initiate Final Replication: Complete the final replication and synchronization of on-premises VMs with Azure.
Perform Cutover: Stop the on-premises VMs, perform the final cutover, and start the VMs in Azure.
Verify Migration: Verify the functionality and performance of VMs in Azure to ensure successful migration.
9 | Post-Migration Activities:
Optimize Performance: Apply any necessary performance optimization in Azure.
Update DNS and Networking: Ensure DNS settings and network configurations are adjusted appropriately to reflect the changes.
Backup and DR Plans: Set up backup and disaster recovery strategies in Azure.

## Factory Inputs
RACI Document:
RACI
Sno | Pre- Migration | Owner
1 | Check able to login with Domain ID -- During Test Migration MS will validate the local creds | Factory
2 | Bastion, RDP needs to be enabled on test virtual network -- This is for validating local credentials | Factory
3 | Check SanDisk Policy ( if it is offline , inform customer to make online) | Factory
3 | Check the Resource Group Locks: | Factory
4 | Check subscription Quotas | Factory
5 | Target server information details | Partner | I Do not see any excel having target info

## Factory Runbook - Inputs
17th March 2026
Migration Runbook- Fraserhealth.ca Website
Planned Start Date | Planned end date | T-Minus | Actual Start Date | Actual end date | Delay | Activities | Duration (in Minutes) | Status | KPMG | FHA | PHSA | App team | Microsoft | Dependencies | Comments | Assumption
2025-11-06 | 2025-11-06 | -93 | 2025-11-06 | 2025-11-18 | 11 - days | App Owner KickOff meeting |  | Completed
2025-11-06 | 2025-11-06 |  | 2025-11-06 | 2025-11-06 |  | Provide an overview of the migration project, including its goals, scope, key milestones, roles and responsibilities. |  | Completed | R | A |  | C,I
2025-11-06 | 2025-11-06 |  | 2025-11-17 | 2025-11-18 |  | Send the application intake form to the application team. |  | Completed | R,A | C,I |  | R
2025-11-17 | 2025-11-20 | -78 | 2025-11-17 | 2025-11-21 | 1 - day | App Intake and Assess current state architecture |  | Completed
2025-11-17 | 2025-11-18 |  | 2025-11-17 | 2025-11-17 |  | Gather details on the existing infrastructure, architecture, and any dependencies. |  | Completed | A | C,I | C,I | R |  | KPMG is dependent on the application team
2025-11-18 | 2025-11-20 |  | 2025-11-19 | 2025-11-21 |  | Evaluate the current architecture, dependencies, hardware/software requirements, and performance of each application. |  | Completed | C,I | A | C | R |  | KPMG is dependent on the application team and FHA
2025-12-12 | 2026-01-06 | -54 | 2026-01-22 | 2026-01-22 | 11 - days | Initial Communication to all (FHA/AppOwners/MS) |  | Completed
2025-12-12 | 2026-01-06 |  | 2026-01-22 | 2026-01-22 |  | Send out a formal communication regarding the migration events,dates planned and requesting the app team to prepare the UAT test cases. |  | Completed | R,A | I |  | C,I | I
2024-12-06 | 2026-01-07 | -50 | 2025-12-12 | 2026-01-16 | 8 - days | Target state Architecture review and approval (Non-Prod) |  | Completed
2024-12-06 | 2025-12-06 |  | 2025-12-12 | 2025-12-12 |  | Create reference target architecture - Subscription design, Network design and application infrastructure. |  | Completed | R,A | I | I | I | C
2026-01-07 | 2026-01-07 |  | 2025-12-18 | 2026-01-16 |  | Reference Architecture design review and Signoff |  | Completed | C,I | R,A | R | R | C | KPMG is dependent on the application team and FHA to provide signoff
2026-01-07 | 2026-01-09 | -47 | 2025-12-22 |  | 0 | Approval Mail from App Owner for Non Prod Migration |  | Inprogress
2026-01-07 | 2026-01-08 |  | 2025-12-22 | 2025-12-22 |  | Send out a formal communication regarding the migration events,dates planned and requesting the app team to approve it |  | Completed | R,A | I |  | C,I | I
2026-01-08 | 2026-01-09 |  | 2025-12-23 |  |  | Get the confirmation mail from the app owner about the migration date |  | Inprogress | R | A | C,I |  | I | KPMG is dependent on the microsoft team to setup the azure migrate appliance
2026-01-12 | 2026-01-14 | -42 | 2026-01-19 | 2026-01-28 |  | Azure Platform setup -Non Prod |  | Completed
2026-01-12 | 2026-01-14 |  | 2025-11-12 | 2025-11-12 |  | Creation of Subscription(s) |  | Completed | A | R | I | I | C,I | KPMG team will be dependent on Landing Zone Creation
2026-01-12 | 2026-01-14 |  | 2026-01-19 | 2026-01-19 |  | Deploy application specific Resource Group |  | Completed | R,A | I | I |  | C
2026-01-12 | 2026-01-14 |  | 2025-11-12 | 2025-11-12 |  | Creation of Target Vnet |  | Completed | C,I | R,A | I | I | C | KPMG team will be dependent on Landing Zone Creation
2026-01-12 | 2026-01-14 |  | 2026-01-27 | 2026-01-28 |  | Creation of Target IP |  | Completed | R,A | I | I |  | C
2026-01-12 | 2026-01-14 |  | 2026-01-20 | 2026-01-21 |  | Provision the Isolated Vnet for testing |  | Completed | C,I | R,A | I | I | C | KPMG team will be dependent on Landing Zone Creation
2026-01-12 | 2026-01-14 |  | 2025-11-12 | 2025-11-12 |  | Provision application/web/DB subnets |  | Completed | C,I | R,A | I | I | C | KPMG team will be dependent on Landing Zone Creation
2026-01-12 | 2026-01-14 |  | 2025-11-12 | 2025-11-12 |  | Creation of application gateway |  | Completed | C,I | R,A | I | I | C | KPMG team will be dependent on Landing Zone Creation
2026-01-12 | 2026-01-14 |  | 2026-01-19 | 2026-01-19 |  | Provision the Azure Key Vault |  | Completed | R,A | I | I | C,I | C,I
2026-01-12 | 2026-01-14 |  | 2026-01-19 | 2026-01-19 |  | Provision the Azure Recovery Services Vault and configure backup policies for the application |  | Completed | R,A | I | I | I | I
2025-12-16 | 2026-01-19 | -41 | 2025-12-19 | 2026-01-16 | 0 | Migration Runbook - Review & Approval(Non-prod) |  | Completed
2025-12-16 | 2025-12-18 |  | 2025-12-17 | 2025-12-17 |  | Create the Migration Runbook |  | Completed | R,A | I | I | I | C
2025-12-18 | 2025-12-19 |  | 2025-12-19 | 2026-01-16 |  | Get the Migration runbook reviewed & Signoff |  | Completed | A | R | I | I | C,I | KPMG is dependent on the application team and FHA to provide signoff
2025-12-18 | 2026-01-19 | -41 |  |  |  | Notify MS to Initiate the Replication of servers in Azure Migrate |  | Yet-to-start
2025-12-18 | 2026-01-19 |  |  |  |  | Select servers for replication in Azure Migrate. |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2025-12-18 | 2026-01-19 |  |  |  |  | Configure replication settings (target region, resource group,VNet,Avalialblity Zone,Vm Size etc). |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2025-12-18 | 2026-01-19 |  |  |  |  | Start initial replication to Azure. |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2025-12-18 | 2026-01-19 |  |  |  |  | Monitor replication until status is Healthy. |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-01-23 | 2026-01-27 | -36 | 2026-01-20 |  |  | Firewall Opening Request, Local User Account & Server Restart Request |  | Inprogress
2026-01-23 | 2026-01-24 |  | 2026-01-20 |  |  | Send Request to PHSA to create the Local User account & Restart the server |  | Inprogress | R,A | I | I | I | I
2026-01-24 | 2026-01-25 |  | 2026-01-20 |  |  | Send Request to PHSA to open the required firewall ports |  | Inprogress | C | A | R | I | I | KPMG is dependent on PHSA and FH
2026-01-25 | 2026-01-27 |  | 2026-01-20 |  |  | Create Local User Account |  | Inprogress | C | A | R | I | I | KPMG is dependent on PHSA and FH
2026-01-27 | 2026-01-27 |  | 2026-01-20 |  |  | Restart Servers |  | Inprogress | C | A | R | I | I | KPMG is dependent on PHSA and FH
2026-01-28 | 2026-01-28 | -34 |  |  |  | Test-Migration execution of Non prod |  | Yet-to-start
Migration bridge will be live on Teams during the test migration -- relevant team members must join - All the below activities will be performed during the call
2026-01-28 | 2026-01-28 |  |  |  |  | Initiate test Migration for replicated servers |  | Yet-to-start | A | I | I | I | R | KPMG is dependent on Microsoft team
2026-01-28 | 2026-01-28 |  |  |  |  | Choose Isolated test virtual network |  | Yet-to-start | A | I | I | I | R | KPMG is dependent on Microsoft team
2026-01-28 | 2026-01-28 |  |  |  |  | Montior the test migration Job and validate the test VM created with test-servername,drives and nic validation |  | Yet-to-start | A | I | I | I | R | KPMG is dependent on Microsoft team
2026-01-31 | 2026-02-03 | -32 | 2025-11-12 |  |  | VM smoke test(Infrastructure Level) |  | Yet-to-start
2026-01-31 | 2026-01-31 |  | 2025-11-12 | 2025-11-12 |  | Configure Bastion Host to provide access to Vms. |  | Completed | I | R,A | I | I | C,I
2026-02-01 | 2026-02-01 |  |  |  |  | Validate the server is up & running, VM boot diagnostics and IP attached, Check the performance of the server(VM performance will be done by KPMG). |  | Yet-to-start | R | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-01 | 2026-02-01 |  |  |  |  | Perform Infra level test on migrated VMs -Follow checks from Smoke Test Tab -- need to validate RACI in smoke test tab |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-02 | 2026-02-02 |  |  |  |  | Document test results (smoke test tab activities will be documented) line 50 - 51 will be merged and mentioned as only boot diagnostics will be checked by MS. |  | Yet-to-start | A | I | I | I | R | KPMG is dependent on Microsoft team
2026-02-03 | 2026-02-03 |  |  |  |  | Delete test VM after validation. |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-03 | 2026-02-03 |  |  |  |  | Confirm replication remains intact for final migration. |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-03 | 2026-02-05 | -30 |  |  |  | Notify users/app team for downtime |  | Yet-to-start
2026-02-03 | 2026-02-05 |  |  |  |  | Send out a formal communication regarding the cutover and the unavailability of the application during the timeframe. |  | Yet-to-start | R,A | I | I | C,I | I
2026-02-06 | 2026-02-08 | -29 |  |  |  | Validate the Replication status is healthy and ensure there are no critical errors prior to the day before migration |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 | -25 |  |  |  | Non-Prod Migration Execution |  | Yet-to-start
2026-02-09 | 2026-02-09 |  |  |  |  | Stop any scheduled backups or jobs on the source VM if required for consistency. |  | Yet-to-start | I | I | R,A | R | I | KPMG is dependent on PHSA and App team
2026-02-09 | 2026-02-09 |  |  |  |  | Perform final backup of on-premise Non-prod servers |  | Yet-to-start | C,I | C,I | R,A | R | I | KPMG is dependent on PHSA and App team
2026-02-09 | 2026-02-09 |  |  |  |  | Verify replication status is Healthy in Azure Migrate. | 10 | Yet-to-start | C,I | I | I |  | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Validate the target settings like : Target region,RG,VMSIZE,Zone,Target Vnet,Subnet mainly | 15 | Yet-to-start | R | C,I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Make sure that atleast one member of on-prem domain admins involved in migration have rdp access to azure migrated VMs (This is required, so that domain admins can login to azure vm post migration and add the machine to the domain | 15 | Yet-to-start | C,I | C,I | R,A |  | I | KPMG is dependent on PHSA
2026-02-09 | 2026-02-09 |  |  |  |  | In Azure Migrate, select the replicated server and choose Migrate → Cutover. | 5 | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Select Shutdown source VM option in Azure Migrate | 10 | Yet-to-start | C,I | I | R | I | R,A | KPMG is dependent on PHSA to shut down on-prem servers
2026-02-09 | 2026-02-09 |  |  |  |  | Start the cutover process; Non- prod DB and Web Servers (SDAPPRESP001, SDDBSRESP001) Azure will create the VM in the target resource group and virtual network as per the replicated settings defined earlier. | 60 | Yet-to-start | C,I | C,I | C,I | I | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Validate the new VM created in Azure Portal | 10 | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Validate Boot status is up and running | 15 | Yet-to-start | R | I | I |  | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Replace the NIC on the migrated VM with the exsiting original static IP by removing the NIC that was automatically created during migration | 30 | Yet-to-start | C,A | I |  | I | R | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Rollback - For Roll back please refer to the Rollback steps section in the T-Zero Cutover Activities tab. | 30 | Yet-to-start | R | C,I | R,A | R | R | KPMG is dependent on PHSA, Microsoft and App team
2026-02-09 | 2026-02-09 | -25 |  |  |  | Post Migration Activities |  | Yet-to-start
2026-02-09 | 2026-02-09 |  |  |  |  | Once the vm is migrated successfully and power down, please change the memory to 4 MB. This will prevent the vm to be powered on by accident. | 30 | Yet-to-start | I | R,A
2026-02-09 | 2026-02-09 |  |  |  |  | Post-migration on vCenter, the vCenter administrators should rename the server display name extenstion to .amig and uncheck the NIC. This step is required immediately after migration; otherwise, HARDNS or DRS may automatically initiate a power-on | 30 | Yet-to-start | I | R,A
2026-02-09 | 2026-02-09 |  |  |  |  | Configure Backup Policies & attach VMs to the backup Policies & Connet to azure monitor if required -- MS will not perform backup activities | 30 | Yet-to-start | C,A | R |  | I | C,I | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Delete the Vmware Tools and any other softwares that are not required. -- SCript can be provided by MS(pod 3) any changes to the script Cx need to make it and need permission to run it in azure. | 15 | Yet-to-start | R | C,I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | Verify the integrity and completeness of data migrated to Azure | 15 | Yet-to-start | R | C,I | I | R | R,A | KPMG is dependent on Microsoft team
2026-02-09 | 2026-02-09 |  |  |  |  | After migration, Domain Admin or Local Admin logs in to migrated Azure servers to validate the authentication of the credntials | 30 | Yet-to-start | C,I | C,I | R,A | R | C,I | KPMG is dependent on PHSA and App team
2026-02-09 | 2026-02-09 |  |  |  |  | Perform Infralevel testing once vm created using Local admin account |  | Yet-to-start | R,A | I | I | I | C,I
2026-02-09 | 2026-02-09 |  |  |  |  | Modify DNS entry for the Azure Vms with their private ip (if required) | 30 | Yet-to-start | C,I | C,I | R,A | I | C,I | KPMG is dependent on PHSA
2026-02-09 | 2026-02-09 |  |  |  |  | Join the VMs to Domain | 30 | Yet-to-start | C,I | C,I | R,A | I | I | KPMG is dependent on PHSA
2026-02-09 | 2026-02-09 |  |  |  |  | Verify the ports and firewall rule on NSG for the Azure migrated DB and Web server | 15 | Yet-to-start | R,A | I | I |  | C,I
2026-02-09 | 2026-02-09 |  |  |  |  | Update integration configuration to point to the new cloud application | 20 | Yet-to-start | C,I | A | I | R | C,I | Kpmg is dependent on app team and FHA
2026-02-09 | 2026-02-09 |  |  |  |  | Ensure user have been granted access to the newly migrated applications | 10 | Yet-to-start | I | A | C,I | R | I | Kpmg is dependent on app team and FHA
2026-02-09 | 2026-02-09 |  |  |  |  | Add the vm to to backendpool of any loadbalancer if required,Associate NSG,ASG | 20 | Yet-to-start | R,A | R |  | I | C,I
2026-02-09 | 2026-02-09 |  |  |  |  | Verify access to the vendor/application team |  | Yet-to-start | C | C | I | R,A | I | Kpmg is dependent on app team |  | The application team will be deploying the application and they will login into the VM via Bastion using their domain ID
2026-02-09 | 2026-02-09 |  |  |  |  | If any, reconfigure the Connection strings, integrations to point to the new environment. This might involve updating API endpoints, re-authenticating, or changing configurations. |  | Yet-to-start | C,I | C,I | I | R,A | I | Kpmg is dependent on app team
2026-02-09 | 2026-02-09 |  |  |  |  | Conduct end-to-end testing of each integration to verify they are working as expected. |  | Yet-to-start | C,I | C,I | I | R,A | I | Kpmg is dependent on app team
2026-02-09 | 2026-02-09 |  |  |  |  | Ensure UAT test cases are created upfront to perform the testing |  | Yet-to-start | C,I | C,I | I | R,A | I | Kpmg is dependent on app team
2026-02-09 | 2026-02-09 |  |  |  |  | Execute test cases and document results. |  | Yet-to-start | C,I | C,I | I | R,A | I | Kpmg is dependent on app team
2026-02-09 | 2026-02-09 |  |  |  |  | Document any issues or deviations found during the testing process |  | Yet-to-start | C,I | C,I | I | R,A | I | Kpmg is dependent on app team
2026-02-09 | 2026-02-09 |  |  |  |  | Request Partial Sign off from app owners (One week lead time to validate the performance testing to provide the complete sign off) |  | Yet-to-start | R,A | I | I |  | C,I
2026-02-09 | 2026-02-12 | -23 |  |  |  | Performance & Application Stability testing by application team |  | Yet-to-start
2026-02-09 | 2026-02-12 |  |  |  |  | One week lead time to montior the performance & Stability of the application by app owners |  | Yet-to-start | C,I | C,I | I | R,A | I | Kpmg is dependent on app team
2026-02-09 | 2026-02-12 | -23 |  |  |  | User Acceptance Prod Env & Notify Stakeholders of Successful Migration |  | Yet-to-start
2026-02-09 | 2026-02-12 |  |  |  |  | Get the UAT signoff & Communicate all the stakeholders about the successful migration. |  | Yet-to-start | R,A | I | I | I | I
2026-02-14 | 2026-02-14 | -21 |  |  |  | Stop replication in Azure Migrate to finalize migration only after we receive signoff by application team | 10 | Yet-to-start | C,I | I |  |  | R,A | KPMG is dependent on Microsoft team
Prod Activities
2025-12-06 | 2026-02-13 | -22 | 2025-12-12 | 2026-01-16 |  | Target state Architecture review and approval (Prod) |  | Completed
2025-12-06 | 2025-12-24 |  | 2025-12-12 | 2025-12-12 |  | Create reference target architecture - Subscription design, Network design and application infrastructure. |  | Completed | R,A | I |  | I | C
2025-12-24 | 2026-02-13 |  | 2025-12-18 | 2026-01-16 |  | Reference Architecture design review and Signoff |  | Completed | C,I | R,A | R | R | C | KPMG is dependent on the application team and FHA to provide signoff
2026-02-13 | 2026-02-16 | -21 | 2026-01-22 | 2026-01-22 |  | Creation of MOP/Review & Signoff(Prod) |  | Completed
2026-02-13 | 2026-02-16 |  | 2026-01-22 | 2026-01-22 |  | Document MOP for RFC creation |  | Completed | R | A | C,I |  | I
2026-02-16 | 2026-02-17 | -20 |  |  |  | RFC Creation & Approval (Prod) |  | Yet-to-start
2026-02-16 | 2026-02-17 |  |  |  |  | Creation of RFC for prod |  | Yet-to-start | R | A | C,I |  | I
2026-01-17 | 2026-02-20 | -17 | 2025-11-12 | 2026-01-28 |  | Azure Platform setup -Prod |  | Completed
2026-01-17 | 2026-02-20 |  | 2025-11-12 | 2025-11-12 |  | Creation of Subscription(s) |  | Completed | A | R | I | I | C,I | Depending on Landing Zone Creation
2026-01-17 | 2026-02-20 |  | 2026-01-28 | 2026-01-28 |  | Deploy application specific Resource Group |  | Completed | R,A | I | I |  | C
2026-01-17 | 2026-02-20 |  | 2025-11-12 | 2025-11-12 |  | Creation of Target Vnet |  | Completed | C,I | R,A | I | I | C | Depending on Landing Zone Creation
2026-01-17 | 2026-02-20 |  | 2026-01-28 | 2026-01-28 |  | Creation of Target IP |  | Completed | R,A | I | I |  | C
2026-01-17 | 2026-02-20 |  | 2026-01-20 | 2026-01-21 |  | Create the Isolated Vnet for testing |  | Completed | C,I | R,A | I | I | C | KPMG team will be dependent on FH to create vNets
2026-01-17 | 2026-02-20 |  | 2025-11-12 | 2025-11-12 |  | Provision application/web/DB subnets |  | Completed | C,I | R,A | I | I | C | Depending on Landing Zone Creation
2026-01-17 | 2026-02-20 |  | 2025-11-12 | 2025-11-12 |  | Creation of application gateway |  | Completed | C,I | R,A | I | I | C | Depending on Landing Zone Creation
2026-01-17 | 2026-02-20 |  | 2026-01-28 | 2026-01-28 |  | Provision the Azure Key Vault |  | Completed | R,A | I | I | C,I | C,I
2026-01-17 | 2026-02-20 |  | 2026-01-28 | 2026-01-28 |  | Provision the Azure Recovery Services Vault and configure backup policies for the application |  | Completed | R,A | C,I | I | I | I
2026-02-20 | 2026-02-23 | -16 | 2025-12-19 | 2026-01-16 |  | Migration Runbook - Review & Approval(prod) |  | Completed
2026-02-20 | 2026-02-23 |  | 2025-12-19 | 2025-12-19 |  | Create the Migration Runbook |  | Completed | R,A | I | I | I | C
2026-02-20 | 2026-02-23 |  | 2025-12-19 | 2026-01-16 |  | Get the Migration runbook reviewed & Signoff |  | Completed | A | R | I | I | C,I | KPMG is dependent on the application team and FHA to provide signoff
2026-02-20 | 2026-02-23 | -16 |  |  |  | Notify MS to Initiate the Replication of servers in Azure Migrate |  | Yet-to-start
2026-02-20 | 2026-02-21 |  |  |  |  | Select servers for replication in Azure Migrate. |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-22 | 2026-02-23 |  |  |  |  | Configure replication settings (target region, resource group,VNet,Avalialblity Zone,Vm Size etc). |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-22 | 2026-02-23 |  |  |  |  | Start initial replication to Azure. |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-22 | 2026-02-23 |  |  |  |  | Monitor replication until status is Healthy. |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-02-24 | 2026-02-27 | -12 |  |  |  | Firewall Opening Request, Local User Account & Server Restart Request |  | Yet-to-start
2026-02-24 | 2026-02-25 |  |  |  |  | Send Request to PHSA to create the Local User account & Restart the server |  | Yet-to-start | R,A | I | I | I | I
2026-02-25 | 2026-02-26 |  |  |  |  | Send Request to PHSA to open the required firewall ports |  | Yet-to-start | C | A | R | I | I | KPMG is dependent on PHSA and FH
2026-02-26 | 2026-02-27 |  |  |  |  | Create Local User Account |  | Yet-to-start | C | A | R |  | I | KPMG is dependent on PHSA and FH
2026-02-25 | 2026-02-27 |  |  |  |  | Restart Servers |  | Yet-to-start | C | A | R |  | I | KPMG is dependent on PHSA and FH
2026-03-04 | 2026-03-06 | -7 |  |  |  | Test-Migration execution of Prod in Isolated Network |  | Yet-to-start
Migration bridge will be live on Teams during the test migration -- relevant team members must join - All the below activities will be performed during the call
2026-03-04 | 2026-03-06 |  |  |  |  | Initiate test Migration for replicated servers |  | Yet-to-start | A | I | I | I | R | KPMG is dependent on Microsoft team
2026-03-04 | 2026-03-06 |  |  |  |  | Choose the isolated virtual network for test migration |  | Yet-to-start | A | I | I | I | R | KPMG is dependent on Microsoft team
2026-03-04 | 2026-03-06 |  |  |  |  | Montior the test migration Job and validate the test VM created with test-servername,drives and nic validation |  | Yet-to-start | A | I | I | I | R | KPMG is dependent on Microsoft team
2026-03-06 | 2026-03-09 | -6 |  |  |  | VM smoke test (Infra-Level) |  | Yet-to-start
2026-03-06 | 2026-03-06 |  | 2025-11-12 | 2025-11-12 |  | Configure Bastion Host to provide access to Vms. |  | Completed | I | R,A | I | I | C,I | KPMG team will be dependent on Landing Zone Creation
2026-03-06 | 2026-03-06 |  |  |  |  | Grant the requested application team access to Azure VMs through Bastion and add them to respective groups on VM | 10 | Yet-to-start | C,I | R,A |  | I | C,I | kPMG is dependent on FH
2026-03-06 | 2026-03-06 |  |  |  |  | Validatethe server is up & running, VM boot diagnostics and IP attached, Check the performance of the server. | 10 | Yet-to-start | R,A | I | I | I | C,I
2026-03-06 | 2026-03-06 |  |  |  |  | Perform Infra level test on migrated VMs -Follow checks from Smoke Test Tab | 20 | Yet-to-start | R,A | I | I | I | C,I | KPMG is dependent on PHSA to shut down on-prem servers
2026-03-09 | 2026-03-09 |  |  |  |  | Document test results (smoke test tab activities will be documented) | 20 | Yet-to-start | R,A | I | I | I | C,I
2026-03-09 | 2026-03-09 |  |  |  |  | Delete test VM after validation. | 10 | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-03-09 | 2026-03-09 |  |  |  |  | Confirm replication remains intact for final migration. | 10 | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-03-09 | 2026-03-11 | -4 |  |  |  | (Go-NoGo) Approval |  | Yet-to-start
2026-03-09 | 2026-03-11 |  |  |  |  | Present the findings from the post-migration phase. This should cover: > Overview of the migration process. > Testing results and whether the success criteria were met. > Issues encountered and their resolution. > User and stakeholder feedback. > Backup and rollback plan status. |  | Yet-to-start | C,I | R,A | I | C | I | KPMG is dependent on FH
2026-03-11 | 2026-03-12 | -3 |  |  |  | Notify users/app team for downtime |  | Yet-to-start
2026-03-11 | 2026-03-12 |  |  |  |  | Send out a formal communication regarding the cutover and the unavailability of the application during the timeframe. |  | Yet-to-start | R,A | I |  | C,I | I
2026-03-12 | 2026-03-16 | -3 |  |  |  | Validate the Replication status is healthy and ensure there are no critical errors prior to the day before migration |  | Yet-to-start | C,I | I | I | I | R,A | KPMG is dependent on Microsoft team
2026-03-17 | 2026-03-17 | 0 |  |  |  | Prod Cutover and post migration tasks |  | Yet-to-start
2026-03-17 | 2026-03-17 |  |  |  |  | Refer to activites in "T-Zero Cutover Activities" tab |  | Yet-to-start |  |  |  |  | R | KPMG is dependent on Microsoft team
2026-03-17 | 2026-03-17 |  |  |  |  | Configure Backup Policies & attach VMs to the backup Policies & Connet to azure monitor if required | 30 | Yet-to-start | C,A | R |  | I | R | KPMG is dependent on Microsoft team and FH
2026-03-17 | 2026-03-17 |  |  |  |  | Replace the NIC on the migrated VM with the exsiting original static IP by removing the NIC that was automatically created during migration | 30 | Yet-to-start | C,A | I |  | I | R | KPMG is dependent on Microsoft team
2026-03-17 | 2026-03-17 |  |  |  |  | Delete the Vmware Tools and any other softwares that are not required. | 15 | Yet-to-start | R | C,I | I | I | R,A | KPMG is dependent on Microsoft team
2026-03-17 | 2026-03-17 |  |  |  |  | Verify the integrity and completeness of data migrated to Azure | 15 | Yet-to-start | R | C,I | I | R | R,A | KPMG is dependent on Microsoft team
2026-03-17 | 2026-03-17 |  |  |  |  | After migration, Domain Admin or Local Admin logs in to migrated Azure servers to validate the authentication of the credntials | 30 | Yet-to-start | C,I | C,I | R,A | R | C,I | KPMG is dependent on PHSA and app team
2026-03-17 | 2026-03-17 |  |  |  |  | Perform Infralevel testing once vm created using Local admin account |  | Yet-to-start | R,A | I | I | I | C,I
2026-03-17 | 2026-03-17 |  |  |  |  | Modify DNS entry for the Azure Vms with their private ip (if required) | 30 | Yet-to-start | C,I | C,I | R,A | I | C,I | KPMG is dependent on PHSA
2026-03-17 | 2026-03-17 |  |  |  |  | Join the VMs to Domain | 30 | Yet-to-start | C,I | C,I | R,A | I | I | KPMG is dependent on PHSA
2026-03-17 | 2026-03-17 |  |  |  |  | Verify the ports and firewall rule on NSG for the Azure migrated DB and Web server | 15 | Yet-to-start | R,A | I | I |  | C,I
2026-03-17 | 2026-03-17 |  |  |  |  | Update integration configuration to point to the new cloud application | 20 | Yet-to-start | C,I | A | I | R | C,I | KPMG is dependent on FH and app team
2026-03-17 | 2026-03-17 |  |  |  |  | Ensure user have been granted access to the newly migrated applications | 10 | Yet-to-start | I | A | C,I | R | I | KPMG is dependent on FH and app team
2026-03-17 | 2026-03-17 |  |  |  |  | Add the vm to to backendpool of any loadbalancer if required,Associate NSG,ASG |  | Yet-to-start | R,A | R |  | I | C,I | KPMG is dependent on FH
2026-03-17 | 2026-03-17 |  |  |  |  | Verify access to the vendor/application team |  | Yet-to-start | C | C | I | R,A | I | KPMG is dependent on app team |  | The application team will be deploying the application and they will login into the VM via Bastion using their domain ID
2026-03-17 | 2026-03-17 |  |  |  |  | If any, reconfigure the Connection strings, integrations to point to the new environment. This might involve updating API endpoints, re-authenticating, or changing configurations. |  | Yet-to-start | C,I | C,I | I | R,A | I | KPMG is dependent on app team
2026-03-17 | 2026-03-17 |  |  |  |  | Conduct end-to-end testing of each integration to verify they are working as expected. |  | Yet-to-start | C,I | C,I | I | R,A | I | KPMG is dependent on app team
2026-03-17 | 2026-03-17 |  |  |  |  | Ensure UAT test cases are created upfront to perform the testing |  | Yet-to-start | C,I | C,I | I | R,A | I | KPMG is dependent on app team
2026-03-17 | 2026-03-17 |  |  |  |  | Execute test cases and document results. |  | Yet-to-start | C,I | C,I | I | R,A | I | KPMG is dependent on app team
2026-03-17 | 2026-03-17 |  |  |  |  | Document any issues or deviations found during the testing process |  | Yet-to-start | C,I | C,I | I | R,A | I | KPMG is dependent on app team
2026-03-17 | 2026-03-17 |  |  |  |  | Request Partial Sign off from app owners (One week lead time to validate the performance testing to provide the complete sign off)
2026-03-17 | 2026-03-17
2026-03-17 | 2026-03-24 | 5 |  |  |  | Performance & Application Stability testing by application team |  | Yet-to-start
2026-03-17 | 2026-03-24 |  |  |  |  | One week lead time to montior the performance & Stability of the application by app owners |  | Yet-to-start | C,I | C,I | I | R,A | I | KPMG is dependent on app team
2026-03-17 | 2026-03-24 | 5 |  |  |  | User Acceptance Prod Env & Notify Stakeholders of Successful Migration |  | Yet-to-start
2026-03-17 | 2026-03-24 |  |  |  |  | Get the UAT signoff & Communicate all the stakeholders about the successful migration. |  | Yet-to-start | R,A | I | I | I | I
2026-03-25 | 2026-03-25 | 6 |  |  |  | Stop replication in Azure Migrate to finalize migration only after we receive signoff by application team | 10 | Yet-to-start | C,I | I |  |  | R,A | KPMG is dependent on Microsoft team
2026-03-25 | 2026-03-26 | 7 |  |  |  | Lesson Learned |  | Yet-to-start
2026-03-25 | 2026-03-26 |  |  |  |  | Facilitate a structured discussion to identify what went well, what didn’t go well, and areas for improvement. |  | Yet-to-start | R,A | I | I | C | C,I
2026-03-26 | 2026-03-30 | 9 |  |  |  | Knowledge transfer and Transition |  | Yet-to-start
2026-03-26 | 2026-03-30 |  |  |  |  | Formal knowledge transfer sessions with FH cloud support team. |  | Yet-to-start | R,A | R,C | I | I | I
2026-03-26 | 2026-03-30 |  |  |  |  | Formally hand over the system from the migration team to the operational team. Ensure all relevant documentation and access permissions are transferred. |  | Yet-to-start | R,A | C |  | I | A | KPMG is dependent on the operational team to provide signoff
2026-03-30 | 2026-03-31 | 10 |  |  |  | Provide Transition Support |  | Yet-to-start
2026-03-30 | 2026-03-31 |  |  |  |  | Monitor system performance and resolve any issues. |  | Yet-to-start | C | R,A | I | C | I | KPMG is dependent on FH
2026-03-30 | 2026-03-31 |  |  |  |  | Updating the documentation based on real-time observations during the hyper care phase |  | Yet-to-start | R,A | I |  | C
Note on G49: Parab, Dolly: This point is addressed and changed accordingly in "runbook" tab highlighted in blue
Note on G50: Parab, Dolly: This point is addressed and changed accordingly in "smoke test" tab. Kindly validate the same
Note on G73: Parab, Dolly: This point is addressed and changed accordingly in "runbook" tab highlighted in blue
Note on G74: Parab, Dolly: This point is addressed and changed accordingly in "runbook" tab highlighted in blue