## Blackout Dates
2024-12-25
2024-12-26 | A
2024-12-27 | C
2024-12-28 | D
2024-12-29 | R
2024-12-30
2024-12-31
2025-01-01
2025-01-17

## T-Minus - KAMM Templat (hidden)
FHA App Migration | [23 empty] | OWNERS
T-Minus Schedule | 2023-08-31 |  | Status Legend | Active | A | 0 |  | Complete | C | 1 |  | Delayed | D | 0 |  | At Risk | R | 0 |  | Future Date | DD-MM |  |  | KPMG | K | FHA-Security Team | NS | Google | G | KPMG & FHA | KN | FHA - Application Team | NA | FHA - Network Team | NN | FHA - Infrastructure Team | NI | FHA - CCoE | NC
|  |  | T- Milestone | App Owner KickOff meeting |  | Document repository access |  | App intake form |  | GCP Environment Access (Dev/Test/Prod) |  | Env on-premise Access |  | Target state Architecture design |  | Target state Architecture review and approval |  | Source setup |  | GCP Dev Platform setup |  | Lower Env Migration execution(App) |  | Provide access to App team | Deploy to Non prod Env (GCP) | Deploy latest code to Dev Env |  | Infra Smoke test/Approval |  | Make Changes to code (if needed) as per FHA Guidelines |  | Review Code Changes |  | GCP Non-Prod Platform setup |  | Deploy to Integrated Non- Prod Envi. |  | Test and Validate App Non-Prod Envi. |  | Deploy to Non- PROD |  | Data Migration |  | Non PROD migration Acceptance |  | GCP Prod Platform setup |  | PROD Migration execution(App) |  | Provide access to App team | Deploy to Non prod Env (GCP) | Deploy latest code to Production Env |  | Prod/DR Cutover |  | Prod Smoke/UAT Test |  | Notify of Successful Migration |  | Lesson Learned |  | Provide Hyper-Care |  | Transition
| Owners |  |  | K |  | NA |  | K/NA/NI/NS |  | NI |  | NI |  | K/NI/NA/NS/G |  | NI/NA/NS |  | K/NI |  | K/NI |  | K/NA |  | NA/NS |  | K/NA |  | K/NA |  | NA |  | NA |  | K/NI/NA |  | K/NA/NI |  | K/NA |  | K/NA |  | NI/NA |  | NA/NI/NS |  | NA/NI |  | K/NA |  | NA/NS |  | K/NA |  | K/NA |  | K/NA |  | NA |  | K/NA/NI/NS |  | K |  | K/NA
|  |  | T-Timeline | -36 |  | -33 |  | -30 |  | -25 |  | -24 |  | -23 |  | -22 |  | -21 |  | -20 |  | -19 |  | -18 |  | -17 |  | -16 |  | -15 |  | -14 |  | -13 |  | -12 |  | -11 |  | -10 |  | -9 |  | -8 |  | -6 |  | -5 |  | -4 |  | -3 |  | -2 |  | -1 |  | 0 |  | 1 |  | 14 | 14 | 21 | 14
Application | Target Plat. | Wave | Migration | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S
Charge Master Toolkit (Craneware) | GCE | Wave 0 | 2023-08-31 | 2023-07-12 |  | 2023-07-17 |  | 2023-07-20 |  | 2023-07-27 |  | 2023-07-28 |  | 2023-07-31 |  | 2023-08-01 |  | 2023-08-02 |  | 2023-08-03 |  | 2023-08-04 |  | 2023-08-07 |  | 2023-08-08 |  | 2023-08-09 |  | 2023-08-10 |  | 2023-08-11 |  | 2023-08-14 |  | 2023-08-15 |  | 2023-08-16 |  | 2023-08-17 |  | 2023-08-18 |  | 2023-08-21 |  | 2023-08-23 |  | 2023-08-24 |  | 2023-08-25 |  | 2023-08-28 |  | 2023-08-29 |  | 2023-08-30 |  | 2023-08-31 |  | 2023-09-01 |  | 2023-09-20 |  | 2023-09-29
Sage 50 Accounting | GCE | Wave 0 | 2023-09-05 | 2023-07-17 | C | 2023-07-20 |  | 2023-07-25 |  | 2023-08-01 |  | 2023-08-02 |  | 2023-08-03 |  | 2023-08-04 |  | 2023-08-07 |  | 2023-08-08 |  | 2023-08-09 |  | 2023-08-10 |  | 2023-08-11 |  | 2023-08-14 |  | 2023-08-15 |  | 2023-08-16 |  | 2023-08-17 |  | 2023-08-18 |  | 2023-08-21 |  | 2023-08-22 |  | 2023-08-23 |  | 2023-08-24 |  | 2023-08-28 |  | 2023-08-29 |  | 2023-08-30 |  | 2023-08-31 |  | 2023-09-01 |  | 2023-09-04 |  | 2023-09-05 |  | 2023-09-06 |  | 2023-09-25 |  | 2023-10-04
Practice Innovation Cloud | GCE | Wave 0 | 2023-09-08 | 2023-07-20 |  | 2023-07-25 |  | 2023-07-28 |  | 2023-08-04 |  | 2023-08-07 |  | 2023-08-08 |  | 2023-08-09 |  | 2023-08-10 |  | 2023-08-11 |  | 2023-08-14 |  | 2023-08-15 |  | 2023-08-16 |  | 2023-08-17 |  | 2023-08-18 |  | 2023-08-21 |  | 2023-08-22 |  | 2023-08-23 |  | 2023-08-24 |  | 2023-08-25 |  | 2023-08-28 |  | 2023-08-29 |  | #REF! |  | 2023-08-31 |  | 2023-09-01 |  | 2023-09-04 |  | 2023-09-05 |  | 2023-09-06 |  | 2023-09-07 |  | 2023-09-08 |  | 2023-09-11 |  | 2023-09-28 |  | 2023-10-09
Blackout Dates
Formulas:
App Owner KickOff meeting = WORKDAY([T- Milestone],F7, Blackout_Dates)
Document repository access = WORKDAY([T- Milestone],H7, Blackout_Dates)
App intake form = WORKDAY([T- Milestone],J7, Blackout_Dates)
GCP Environment Access (Dev/Test/Prod) = WORKDAY([T- Milestone],L7, Blackout_Dates)
Env on-premise Access = WORKDAY([T- Milestone],N7, Blackout_Dates)
Target state Architecture design = WORKDAY([T- Milestone],P7, Blackout_Dates)
NI/NA/NS = WORKDAY([T- Milestone],R7, Blackout_Dates)
Source setup = WORKDAY([T- Milestone],T7, Blackout_Dates)
GCP Dev Platform setup = WORKDAY([T- Milestone],V7, Blackout_Dates)
Lower Env Migration execution(App) = WORKDAY([T- Milestone],X7, Blackout_Dates)
Provide access to App team = WORKDAY([T- Milestone],Z7, Blackout_Dates)
Provide access to App team = WORKDAY([T- Milestone],AZ7, Blackout_Dates)
Deploy latest code to Dev Env = WORKDAY([T- Milestone],AB7, Blackout_Dates)
Infra Smoke test/Approval = WORKDAY([T- Milestone],AD7, Blackout_Dates)
NA = WORKDAY([T- Milestone],AF7, Blackout_Dates)
Review Code Changes = WORKDAY([T- Milestone],AH7, Blackout_Dates)
GCP Non-Prod Platform setup = WORKDAY([T- Milestone],AJ7, Blackout_Dates)
Deploy to Integrated Non- Prod Envi. = WORKDAY([T- Milestone],AL7, Blackout_Dates)
Test and Validate App Non-Prod Envi. = WORKDAY([T- Milestone],AN7, Blackout_Dates)
Deploy to Non- PROD = WORKDAY([T- Milestone],AP7, Blackout_Dates)
Data Migration = WORKDAY([T- Milestone],AR7, Blackout_Dates)
Non PROD migration Acceptance = WORKDAY([T- Milestone],AT7, Blackout_Dates)
GCP Prod Platform setup = WORKDAY([T- Milestone],AV7, Blackout_Dates)
GCP Prod Platform setup = WORKDAY([T- Milestone],#REF!, Blackout_Dates)
PROD Migration execution(App) = WORKDAY([T- Milestone],AX7, Blackout_Dates)
PROD Migration execution(App) = WORKDAY([T- Milestone],AV7, Blackout_Dates)
Deploy latest code to Production Env = WORKDAY([T- Milestone],BB7, Blackout_Dates)
Deploy latest code to Production Env = WORKDAY([T- Milestone],AZ7, Blackout_Dates)
Prod/DR Cutover = WORKDAY([T- Milestone],BD7, Blackout_Dates)
Prod/DR Cutover = WORKDAY([T- Milestone],BB7, Blackout_Dates)
Prod Smoke/UAT Test = WORKDAY([T- Milestone],BF7, Blackout_Dates)
Prod Smoke/UAT Test = WORKDAY([T- Milestone],BD7, Blackout_Dates)
Notify of Successful Migration = WORKDAY([T- Milestone],BH7, Blackout_Dates)
Notify of Successful Migration = WORKDAY([T- Milestone],BF7, Blackout_Dates)
Lesson Learned = WORKDAY([T- Milestone],BJ7, Blackout_Dates)
Lesson Learned = WORKDAY([T- Milestone],BH7, Blackout_Dates)
Provide Hyper-Care = WORKDAY([T- Milestone],BL7, Blackout_Dates)
Provide Hyper-Care = WORKDAY([T- Milestone],BJ7, Blackout_Dates)
Transition = WORKDAY([T- Milestone],BN7, Blackout_Dates)
Transition = WORKDAY([T- Milestone],BL7, Blackout_Dates)
Milestone

## T-Minus Schedule- Book a Break
FHA App Migration
| 2025-02-10 | Non-Prod
T-Minus Schedule | 2026-03-17 | Prod |  | Status Legend - S | Complete | C | At Risk | R | Future Date | D | Active | A | [9 empty] | KPMG | K | Fraser health | F | PHSA | P | Microsoft | M | Fraser health App Team | FA | [18 empty] | Fraser health | F
|  |  | App Owner KickOff meeting |  |  | App intake and asses current state architecture |  | Initial Communication to all (FH/App Owner/MS/Vendors) |  | Target state Architecture review and approval |  | Approval Mail from App Owner for Non Prod Migration |  | Azure Platform setup - Non Prod |  | Migration Runbook - Review & Approval(Non-prod) |  | Notify MS to Initiate the Replication of servers in Azure Migrate |  | Firewall Opening Request, Local User Account & Server Restart Request |  | Test-Migration execution of Non prod. |  | VM smoke test (Infra Level) |  | Notify users/app team of downtime |  | Non-Prod Migration Execution |  | Performance & Stability testing by application team |  | User Acceptance Prod Env & Notify Stakeholders of Successful Migration |  | Target state Architecture review and approval (Prod) |  | Creation of MOP/Review & signoff (prod) |  | RFC Creation & approval (prod) |  | Azure Platform setup - Prod |  | Migration Runbook - Review & Approval(Prod) |  | Notify MS to Initiate the Replication of servers in Azure Migrate |  | Firewall Opening Request, Local User Account & Server Restart Request |  | Test-Migration execution of Prod. |  | VM smoke test (Infra Level) |  | (Go - NoGo) Approval |  | Notify users/app team of downtime |  | Prod Cutover and post migration tasks |  | Performance & Stability testing by application team |  | User Acceptance Prod Env & Notify Stakeholders of Successful Migration |  | Lesson-Learned |  | Knowledge transfer and Transition |  | Provide Transition Support
| Owners |  |  | F/K |  | K |  | K |  | K/F/FA |  | K/F |  | K/F/M |  | K/F/FA/M |  | K/M |  | P/K |  | M |  | FA/M/K |  | K |  | M/K |  | FA |  | K |  | K/F/FA |  | K/F |  | F |  | K/F/M |  | F/K/FA/M |  | K/M |  | P/K |  | M |  | FA/M/K |  | FA/F |  | K |  | M/K |  | F |  | K |  | K/F |  | K/F |  | K/F
|  |  | T-Timeline | -93 |  | -83 |  | -50 |  | -49 |  | -47 |  | -44 |  | -41 |  | -41 |  | -35 |  | -34 |  | -30 |  | -28 |  | -26 |  | -23 |  | -23 |  | -22 |  | -21 |  | -20 |  | -17 |  | -16 |  | -16 |  | -12 |  | -7 |  | -6 |  | -4 |  | -3 |  | 0 |  | 5 |  | 5 |  | 7 |  | 9 |  | 10
Application | Target Plat. | Wave | Migration | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S
Book a break (Original Date) | Azure | Wave 1 (Non-Prod) Wave 2 (Prod) | 2026-03-17 | 2025-11-06 | C | 2025-11-20 | C | 2026-01-06 | C | 2026-01-07 | C | 2026-01-09 | C | 2026-01-14 | C | 2026-01-19 | C | 2026-01-19 | A | 2026-01-27 | A | 2026-01-28 | D | 2026-02-03 | D | 2026-02-05 | D | 2026-02-09 | D | 2026-02-12 | D | 2026-02-12 | D | 2026-02-13 | D | 2026-02-16 | D | 2026-02-17 | D | 2026-02-20 | C | 2026-02-23 | D | 2026-02-23 | D | 2026-02-27 | D | 2026-03-06 | D | 2026-03-09 | D | 2026-03-11 | D | 2026-03-12 | D | 2026-03-17 | D | 2026-03-24 | D | 2026-03-24 | D | 2026-03-26 | D | 2026-03-30 | D | 2026-03-31 | D
Book a break (Revised Date)
Formulas:
Status Legend - S = WORKDAY([Migration],F7, Blackout_Dates)
C = WORKDAY([Migration],H7, Blackout_Dates)
R = WORKDAY([Migration],J7, Blackout_Dates)
D = WORKDAY([Migration],L7, Blackout_Dates)
A = WORKDAY([Migration],N7, Blackout_Dates)
K/F/M = WORKDAY([Migration],P7, Blackout_Dates)
K/F/M = WORKDAY([Migration],AP7, Blackout_Dates)
K/F/FA/M = WORKDAY([Migration],R7, Blackout_Dates)
K/M = WORKDAY([Migration],T7, Blackout_Dates)
K/M = WORKDAY([Migration],AT7, Blackout_Dates)
P/K = WORKDAY([Migration],V7, Blackout_Dates)
P/K = WORKDAY([Migration],AV7, Blackout_Dates)
KPMG = WORKDAY([Migration],X7, Blackout_Dates)
Fraser health = WORKDAY([Migration],Z7, Blackout_Dates)
Fraser health = WORKDAY([Migration],AZ7, Blackout_Dates)
PHSA = WORKDAY([Migration],AB7, Blackout_Dates)
Microsoft = WORKDAY([Migration],AD7, Blackout_Dates)
Fraser health App Team = WORKDAY([Migration],AF7, Blackout_Dates)
K = WORKDAY([Migration],AH7, Blackout_Dates)
K = WORKDAY([Migration],BD7, Blackout_Dates)
K/F/FA = WORKDAY([Migration],AJ7, Blackout_Dates)
K/F = WORKDAY([Migration],AL7, Blackout_Dates)
K/F = WORKDAY([Migration],BL7, Blackout_Dates)
F = WORKDAY([Migration],AN7, Blackout_Dates)
F = WORKDAY([Migration],BH7, Blackout_Dates)
F/K/FA/M = WORKDAY([Migration],AR7, Blackout_Dates)
M = WORKDAY([Migration],AX7, Blackout_Dates)
FA/F = WORKDAY([Migration],BB7, Blackout_Dates)
M/K = WORKDAY([Migration],BF7, Blackout_Dates)
Milestone

## T-Minus Schedule - Ivanti (hidden)
FHA App Migration | [13 empty] | OWNERS
T-Minus Schedule | 2025-02-15 |  | Status Legend - S | Active | A | Complete | C | At Risk | R | Future Date | D |  |  |  |  | KPMG | K | FHA | F | PHSA | P | NTT | NT | FH App integration | FA
|  |  | T- Milestone | Finalize Wave applications |  | App Owner KickOff meeting |  | Initial Communication to all (Vendors, CAB, NTT, PHSA) |  | App intake and define current state architecture |  | Target state Architecture review and approval |  | Azure Platform setup Non-Prod |  | KPMG: Migration execution to Non-Prod.; FHA: VM smoke test; PHSA: App configuration and integrations update; NTT: Status Update Communication | NonProd - Data sync |  | Provide access to App team |  | UAT and validation |  | Non-prod Signoff |  | Change review Board approval |  | Azure Platform setup - Prod |  | Migration execution to Prod. |  | VM smoke test |  | Prod Status Update Communication |  | App configuration/integrations update(NTT) |  | Prod - Data sync |  | Provide access to App team |  | User acceptance Test - Prod Env |  | (Go-NoGo) Approval |  | Change review Board approval |  | Notify users/app team of downtime |  | Prod Cutover and post migration tasks |  | Notify Stakeholders of Successful Migration |  | Lesson Learned |  | Provide Hyper-Care |  | Knowledge transfer and Transition
| Owners |  |  | K/F |  | F/K |  | K |  | K |  | K/F |  | K/P |  | KPMG: K; FHA: K; PHSA: FA/NT; NTT: K | K |  | K/F |  | F |  | F |  | F/K |  | K/P |  | K |  | K |  | K |  | FA/NT |  | K |  | K/F |  | F |  | F |  | F/K |  | K |  | K/FA/NTT/PHSA |  | K |  | K/F/PHSA |  | K/F |  | K/F
|  |  | T-Timeline | -55 |  | -55 |  | -50 |  | -44 |  | -39 |  | -27 |  | KPMG: -23; FHA: -22; PHSA: -19; NTT: -19 | -17 |  | -17 |  | -15 |  | -14 |  | -14 |  | -11 |  | -9 |  | -8 |  | -8 |  | -5 |  | -4 |  | -4 |  | -2 |  | -1 |  | -1 |  | -1 |  | 0 |  | 0 |  | 1 |  | 1 |  | 12
Application | Target Plat. | Wave | Migration | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S | T- Date | S
Ivanti | Azure | Wave 1 | 2025-02-14 | 2024-11-20 | D | 2024-11-20 | C | 2024-11-27 | A | 2024-12-05 | A | 2024-12-12 | A | 2025-01-07 |  | KPMG: 2025-01-13; FHA: 2025-01-14; PHSA: 2025-01-20; NTT: 2025-01-20 | 2025-01-22 |  | 2025-01-22 |  | 2025-01-24 |  | 2025-01-27 |  | 2025-01-27 |  | 2025-01-30 |  | 2025-02-03 |  | 2025-02-04 |  | 2025-02-04 |  | 2025-02-07 |  | 2025-02-10 |  | 2025-02-10 |  | 2025-02-12 |  | 2025-02-13 |  | 2025-02-13 |  | 2025-02-13 |  | 2025-02-14 |  | 2025-02-14 |  | 2025-02-17 |  | 2025-02-17 |  | 2025-03-04
Formulas:
Active = WORKDAY([Status Legend - S],F7, Blackout_Dates)
Complete = WORKDAY([Status Legend - S],H7, Blackout_Dates)
At Risk = WORKDAY([Status Legend - S],J7, Blackout_Dates)
Future Date = WORKDAY([Status Legend - S],L7, Blackout_Dates)
Milestone